## Dashboard
Project Name : | Orange HRM
Delivery Date : | 27/6/2025
Release Number : | Release no 01
Designed By : | Nagham,Haya,Abedalrahman,Mohammad
Browsers : | Chrome,Edge,Brave
Android Versions : | -
iOS Versions : | -
Total Number of Test Cases : | 302
Number of Passed Test Cases : | 287
Number of Failed Test Cases : | 15
Number of Blocked Test Cases : | 1
Environment : | Windows 11,10

## Test Cases (Employee)
Test Suite ID | Title | Test Case ID | Test Case Descriprion | Precondition | Test Data | Test Steps | Expected Result | Actual Result | Status
"3.0 | LogIn | 3.0.1 | Login with valid credentials | HR Admin has added the user to the system | Username: Mohammad, Password: Mohammad@123 | 1. Navigate to login page 2. Enter valid username 3. Enter valid password 4. Click on Login button | User should be redirected to the Dashboard | User was redirected to the Dashboard correctly | Pass
|  | 3.0.2 | Login with valid username and invalid password | User is on the login page | Username: Mohammad, Password: 1m1o2oj | 1. Navigate to login page 2. Enter valid username 3. Enter invalid password 4. Click on Login button | System should display error massage | System displayed 'Invalid credentials' | Pass
|  | 3.0.3 | Login with blank fields | User is on the login page | Username: (blank), Password: (blank) | 1. Navigate to login page 2. Click on Login without entering credentials | System should show 'Required' message for both fields | System displayed 'Required' under both fields | Pass
|  | 3.0.4 | Login with capital letters in username | User is on the login page | Username: MOHAMMAD, Password: Mohammad@123 | 1. Navigate to login page 2. Enter capitalized username 3. Enter valid password 4. Click Login | User should be redirected to the Dashboard | User was redirected to the Dashboard correctly | Pass
|  | 3.0.5 | Login with spaces in username | User is on the login page | Username: " Mohammad ", Password: Mohammad@123 | 1. Navigate to login page 2. Enter username with spaces 3. Enter valid password 4. Click Login | System should trim spaces and redirect to Dashboard | User was redirected to the Dashboard correctly | Pass
|  | 3.0.6 | Password field hides input | User is on the login page |  | 1. Navigate to login page 2. Focus on password field 3. Type characters | Input should be masked with asterisks | Password was hidden properly | Pass
|  | 3.0.7 | Login from different browsers | User has valid credentials | Username: Mohammad, Password: Mohammad@123 | 1. Open login page in different browsers (e.g. Chrome, Firefox) 2. Enter credentials 3. Click Login | User should be logged in successfully in all browsers | Login succeeded in all browsers | Pass
|  | 3.0.8 | Login with invalid username | User is on the login page | Username: test76767, Password: Mohammad@123 | 1. Navigate to login page 2. Enter invalid username 3. Enter valid password 4. Click Login | System should display error massage | System displayed 'Invalid credentials' | Pass
|  | 3.0.9 | Login with non-existing account | User is on the login page | Username: test, Password: test123 | 1. Enter non-existing credentials 2. Click Login | System should display error massage | System displayed 'Invalid credentials' | Pass
|  | 3.0.10 | SQL injection in login fields | User is on the login page | Username: ' OR 1=1-- | 1. Enter SQL code in input fields 2. Click Login | System should treat input as string and reject login | System displayed 'Invalid credentials' | Pass
|  | 3.0.11 | Multiple failed login attempts | User repeatedly enters wrong password | Username: Mohammad, Password: wrong (×5) | 1. Enter wrong password multiple times 2. Observe system behavior | System should lock account or display warning | No action was taken | Fail
|  | 3.0.12 | Using browser back after login | User has logged in | Valid credentials | Navigate back using browser after login | System should not return to login page unless logged out | Login page reappeared but was unresponsive | Fail
|  | 3.0.13 | Username & password not shown in URL | User logs in successfully | Valid credentials | 1. Login successfully 2. Observe URL | URL should not contain username/password | Credentials were not shown in URL | Pass
3.1.1 | Personal Details | 3.1.1.1 | Edit editable personal details | ESS-User logged in successfully. | Full Name, License Expiry Date, Other ID | 1. Access 'My Info' > 'Personal Details' 2. Edit editable fields 3. Click 'Save' | Information should be updated successfully with message 'Successfully Updated' | Information updated successfully with message displayed | Pass
|  | 3.1.1.2 | Verify non-editable fields cannot be modified | ESS-User logged in successfully. | Employee ID, Date of Birth, Driver License | 1. Access 'My Info' > 'Personal Details' 2. Try editing non-editable fields | Fields should be disabled and not editable | Fields were non-editable as expected | Pass
|  | 3.1.1.3 | Leave required fields (First and Last Name) empty | ESS-User logged in successfully | First Name: [blank], Last Name: [blank] | 1. Access 'My Info' > 'Personal Details' 2. Clear First and Last Name 3. Click 'Save' | System should display a messages for the required fields | Validation messages displayed for required fields | Pass
|  | 3.1.1.4 | Leave all optional fields empty and save | ESS-User logged in successfully |  | 1. Access 'My Info' > 'Personal Details' 2. Leave optional fields empty 3. Click 'Save' | Information should be saved successfully | Data saved successfully | Pass
|  | 3.1.1.5 | Enter valid License Expiry Date manually | ESS-User logged in successfully | 2020-06-11 | 1. Access 'My Info' > 'Personal Details' 2. Manually enter License Expiry Date 3. Click 'Save' | Date should be accepted and saved successfully | Date accepted and saved | Pass
|  | 3.1.1.6 | Select License Expiry Date using calendar icon | ESS-User logged in successfully | 2020-06-11 | 1. Access 'My Info' > 'Personal Details' 2. Click on calendar icon 3. Select date 4. Click 'Save' | Date should populate and save successfully | Date selected and saved successfully | Pass
|  | 3.1.1.7 | Enter invalid format in License Expiry Date | ESS-User logged in successfully | 00-2-2020 | 1. Access 'My Info' > 'Personal Details' 2. Enter date in wrong format 3. Click 'Save' | System should display error message about incorrect format | Validation error displayed: “Should be a valid date in yyyy-dd-mm format” | Pass
|  | 3.1.1.8 | Select both Male and Female gender | ESS-User logged in successfully |  | 1. Access 'My Info' > 'Personal Details' 2. Try selecting both Male and Female | Only one selection should be allowed | Only one radio button could be selected at a time | Pass
|  | 3.1.1.9 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Access 'My Info' > 'Personal Details' 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.1.10 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.1.11 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.1.12 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.1.13 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.1.14 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.1.15 | Verify 'Records Found' count updates correctly after upload and delete | ESS-User logged in successfully |  | 1. Count current attachments 2. Upload new file 3. Verify count increased 4. Delete a file 5. Verify count decreased | Record count should increase by 1 after upload and decrease by 1 after delete | Count updated correctly | Pass
|  | 3.1.1.16 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.2 | Photograph | 3.1.2.1 | Choose a valid Profile Picture (jpg, png, gif < 1MB) | ESS-User logged in successfully | image.png <1MB | 1. Click on photo area 2. Click '+ icon' 3. Choose a valid picture 4. Click 'Save' | Profile picture should be updated successfully | Profile picture updated successfully | Pass
|  | 3.1.2.2 | Choose invalid profile picture (svg) | ESS-User logged in successfully | image.svg | 1. Click on photo area 2. Click '+ icon' 3. Choose an SVG file 4. Click 'Save' | System should display error message | "File type not allowed" message displayed | Pass
|  | 3.1.2.3 | Click save without choosing any picture | ESS-User logged in successfully | No file selected | 1. Click on photo area 2. Click '+ icon' 3. Click 'Save' without selecting a file | System should display error message | Required message displayed | Pass
|  | 3.1.2.4 | Choose picture > 1MB | ESS-User logged in successfully | image.jpg >1MB | 1. Click on photo area 2. Click '+ icon' 3. Choose a picture larger than 1MB 4. Click 'Save' | System should display error message | "Attachment Size Exceeded" message displayed | Pass
3.1.3 | Contact Details | 3.1.3.1 | Enter valid address details | ESS-User logged in successfully | Street 1: 'sinjel', Street 2: '117', City: 'Ramallah', State: 'Palestine' | 1. Access 'My Info' > 'Contact Details' 2. Enter valid address fields 3. Click 'Save' | Address should be saved successfully | Address saved successfully | Pass
|  | 3.1.3.2 | Enter valid phone numbers within 15 characters | ESS-User logged in successfully | Home: +96261234567 | 1. Access 'My Info' > 'Contact Details' 2. Enter valid numbers 3. Click 'Save' | Phone numbers should be saved successfully | Numbers saved successfully | Pass
|  | 3.1.3.3 | Enter invalid phone number | ESS-User logged in successfully | Mobile: 5 | 1. Access 'My Info' > 'Contact Details' 2. Enter invalid phone format 3. Click 'Save' | System should reject input | Invalid phone accepted | Fail
|  | 3.1.3.4 | Enter valid emails in Work and Other Email fields | ESS-User logged in successfully | admin@example.com | 1. Access 'My Info' > 'Contact Details' 2. Enter valid emails 3. Click 'Save' | Emails should be saved successfully | Emails saved | Pass
|  | 3.1.3.5 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Access 'My Info' > 'Personal Details' 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.3.6 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.3.7 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.3.8 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.3.9 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.3.10 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.3.11 | Verify behavior of "State" field based on selected country | ESS-User logged in successfully | Country = US | 1. Access 'My Info'>'Contact Details' 2. ocate the "Country" dropdown and select United States. | The "State" field should become a dropdown menu with a list of US. States | Field remains manual input for all countries, no dropdown shown. | fail
|  | 3.1.3.12 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.4 | Emergency Contact | 3.1.4.1 | Enter valid Name, Relationship, and Home Telephone | ESS-User logged in successfully | Name: Ahmad, Relationship: Brother, Home Telephone: 0599999999 | 1. Go to 'My Info' > 'Emergency Contacts' 2. Click 'Add' 3. Enter valid values 4. Click 'Save' | Contact should be added with message "Successfully Saved" | Contact saved successfully | Pass
|  | 3.1.4.2 | Enter invalid characters in phone fields | ESS-User logged in successfully | Phone: "123@aسس" | 1. Go to 'Emergency Contacts' 2. Click 'Add' 3. Enter symbols/letters in phone fields 4. Click 'Save' | System should display error massage | "Allows numbers and only + - / ( )" displayed | Pass
|  | 3.1.4.3 | Leave Name, Relationship, and Home Telephone blank | ESS-User logged in successfully | Blank fields | 1. Go to 'Emergency Contacts' 2. Click 'Add' 3. Leave required fields empty 4. Click 'Save' | System should display required message | Required message displayed | Pass
|  | 3.1.4.4 | Edit existing emergency contact using edit icon | ESS-User with existing contact |  | 1. Go to 'Emergency Contacts' 2. Click edit icon next to contact 3. Modify data 4. Click 'Save' | Info should update and message: "Successfully Updated" should appear | Contact updated successfully | Pass
|  | 3.1.4.5 | Delete an emergency contact using delete icon | ESS-User with existing contact |  | 1. Go to 'Emergency Contacts' 2. Click delete icon next to contact 3. Confirm deletion | Message "Successfully Deleted" should appear | Contact deleted successfully | Pass
|  | 3.1.4.6 | Delete all emergency contacts using "Delete Selected" | ESS-User with multiple contacts |  | 1. Go to 'Emergency Contacts' 2. Select all checkboxes 3. Click "Delete Selected" 4. Confirm | Message "Successfully Deleted" should appear | All contacts deleted | Pass
|  | 3.1.4.7 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Access 'My Info' > ' Emergency Contact' 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.4.8 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Access 'My Info' > ' Emergency Contact' > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.4.9 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Access 'My Info' > ' Emergency Contact' > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.4.10 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.4.11 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.4.12 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.4.13 | Verify 'Records Found' count updates correctly after upload and delete | ESS-User logged in successfully |  | 1. Count current attachments 2. Upload new file 3. Verify count increased 4. Delete a file 5. Verify count decreased | Record count should increase by 1 after upload and decrease by 1 after delete | Count updated correctly | Pass
|  | 3.1.4.14 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Access 'My Info' > ' Emergency Contact' > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.5 | Dependents | 3.1.5.1 | Enter valid Name and Relationship (Child or Other with Specify) | ESS-User logged in successfully | Name :Ahmad, Specify"brother" | 1. Go to 'My Info' > 'Dependents' 2. Click 'Add' 3. Enter valid Name 4. Select Relationship 5. If 'Other', enter Specify 6. Click 'Save' | Dependent should be saved with message "Successfully Saved" | Saved as expected | Pass
|  | 3.1.5.2 | Leave required fields empty (Name, Relationship, Specify if Other) | ESS-User logged in successfully | All required fields blank | 1. Go to 'Dependents' 2. Click 'Add' 3. Leave Name, Relationship, or Specify blank 4. Click 'Save' | System should display required message | Required message displayed | Pass
|  | 3.1.5.3 | Enter valid Date of Birth manually | ESS-User logged in successfully | Date: 2010-05-10 | 1. Go to 'Dependents' 2. Enter DOB manually 3. Click 'Save' | Date should be saved successfully | Date saved correctly | Pass
|  | 3.1.5.4 | Select Date of Birth using calendar icon | ESS-User logged in successfully | Date: 2010-05-10 | 1. Go to 'Dependents' 2. Open calendar 3. Select a date 4. Click 'Save' | Date should be saved successfully | Date saved correctly | Pass
|  | 3.1.5.5 | Enter invalid format in Date of Birth | ESS-User logged in successfully | Date: 00/00/2010 | 1. Go to 'Dependents' 2. Enter date in invalid format 3. Click 'Save' | system shold display error massage | system displayed "Should be a valid date in yyyy-dd-mm format" | Pass
|  | 3.1.5.6 | Edit a dependent using edit icon | ESS-User with existing dependent |  | 1. Go to 'Dependents' 2. Click edit icon next to a dependent 3. Modify field 4. Save | System should show "Successfully Updated" | Dependent updated successfully | Pass
|  | 3.1.5.7 | Delete a dependent using delete icon | ESS-User with existing dependent |  | 1. Go to 'Dependents' 2. Click delete icon 3. Confirm deletion | System should show "Successfully Deleted" | Deleted successfully | Pass
|  | 3.1.5.8 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Access 'My Info' > 'Dependents' 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.5.9 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Access 'My Info' > 'Dependents' > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.5.10 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Access 'My Info' > 'Dependents' > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.5.11 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.5.12 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.5.13 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.5.14 | Verify 'Records Found' count updates correctly after upload and delete | ESS-User logged in successfully |  | 1. Count current attachments 2. Upload new file 3. Verify count increased 4. Delete a file 5. Verify count decreased | Record count should increase by 1 after upload and decrease by 1 after delete | Count updated correctly | Pass
|  | 3.1.5.15 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Access 'My Info' > 'Dependents' > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.6 | Immigration | 3.1.6.1 | Enter valid Passport or Visa data | ESS-User logged in successfully | Document: Passport or Visa Number: '123456' Valid dates format | 1. Go to 'Immigration' 2. Click 'Add' 3. Select Passport or Visa 4. Enter valid Number and valid dates 5. Click 'Save' | Immigration record should be saved with message 'Successfully Saved' | Record saved correctly | Pass
|  | 3.1.6.2 | Enter letters in 'Number' field | ESS-User logged in successfully | Number: 'ABCD1234' | 1. Go to 'Immigration' 2. Click 'Add' 3. Enter letters in Number field 4. Click 'Save' | System should reject it and display error message | Letters accepted in Number field | Fail
|  | 3.1.6.3 | Click 'Save' without entering required Number field | ESS-User logged in successfully | Number: [empty] | 1. Go to 'Immigration' 2. Click 'Add' 3. Leave Number empty 4. Click 'Save' | System should display required message | Required message displayed | Pass
|  | 3.1.6.4 | Edit Immigration record using edit icon | ESS-User with existing immigration record |  | 1. Go to 'Immigration' 2. Click edit icon next to record 3. Modify data 4. Click 'Save' | Record should be updated with message 'Successfully Updated' | Record updated correctly | Pass
|  | 3.1.6.5 | Delete Immigration record using delete icon | ESS-User with existing immigration record |  | 1. Go to 'Immigration' 2. Click delete icon next to record 3. Confirm deletion | Record should be deleted with message 'Successfully Deleted' | Record deleted correctly | Pass
|  | 3.1.6.6 | Enter invalid format in any date field (e.g. 00-02-2020) | ESS-User logged in successfully | Issued Date: '00-02-2020' | 1. Go to 'Immigration' 2. Enter invalid date 3. Click 'Save' | System should display error massage | "Should be a valid date in yyyy-dd-mm format" displayed | Pass
|  | 3.1.6.7 | Select Passport and Visa together | ESS-User logged in successfully |  | 1. Try selecting both radio buttons for Passport and Visa | Only one option should be selectable at a time | Only one selection allowed | Pass
|  | 3.1.6.8 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Go to My Info > Immigration 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.6.9 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Go to My Info > Immigration > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.6.10 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Go to My Info > Immigration > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.6.11 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.6.12 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.6.13 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.6.14 | Verify "Issued Date" does not accept future dates | ESS-User logged in successfully | Issued Date = future date (11-11-2025) | 1.Go to My Info > Immigration2. Click on Add3. Enter a future date in the Issued Date field4. Click Save | System should reject future dates and show an error message. | System accepts the future date without any validation. | Fail
|  | 3.1.6.15 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Go to My Info > Immigration > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.7 | Job Details | 3.1.7.1 | verify that the Job button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Log in then Navigate to “My Info” | The Job section should appear to the user | As expected | Pass
|  | 3.1.7.2 | Verify visibility of job information | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “Job” | All job details are displayed correctly | As expected | Pass
|  | 3.1.7.3 | Verify that job fields are not editable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Attempt to click or edit any job detail field | Fields are read-only; no editable fields present | As expected | Pass
|  | 3.1.7.4 | Ensure absence of Edit/Save/Delete buttons | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Check for action buttons in the Job section | No Edit, Save, or Delete buttons exist | As expected | Pass
|  | 3.1.7.5 | Ensure "Include Employment Contract Details" button is clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “Job”→ enable Include Employment Contract Details button | The information of the contract should appear when the user enable the button | As expected | Pass
3.1.8 | Salary | 3.1.8.1 | verify that the slary button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | log in then Navigate to “My Info” | The salary section should appear to the user | As expected | Pass
|  | 3.1.8.2 | Verify visibility of Salary information | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “salary” | All salary details are displayed correctly | As expected | Pass
|  | 3.1.8.3 | Verify salary details section is not editable for EES | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “salary” | information field is completely hidden from the ESS-User | As expected | Pass
|  | 3.1.8.4 | Test direct URL access to salary page | A Browser | RRL : https://opensource-demo.orangehrmlive.com/web/index.php/pim/viewSalaryList/empNumber/7 | Enter direct salary URL in browser | User receives access denied or is redirected | As expected | Pass
3.1.9 | Report To | 3.1.9.1 | verify that the "Report to"button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | log in then Navigate to “My Info” → Look for Report to section | The Report to section should appear to the user | As expected | Pass
|  | 3.1.9.2 | Verify supervisors are listed | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “Report To” section | Supervisor list is displayed | As expected | Pass
|  | 3.1.9.3 | View subordinates if user is also a supervisor | ESS-User is also supervisor | username=nnnnn Password=nnnnn12345 | Navigate to “Report To” → Look for subordinate section | Subordinate list is displayed | As expected | Pass
|  | 3.1.9.4 | Ensure fields are read-only | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Try editing fields like Assigned Supervisor or Subordinate | Fields are disabled BUT not editable | As expected | Pass
3.1.10 | Qualifications | 3.1.10.1 | verify that the "Qualifications"button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | log in then Navigate to “My Info” → Look for Qualifications section | The Report to section should appear to the user | As expected | Pass
|  | 3.1.10.2 | Verify visibility of Qualifications information | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “Qualifications ” | All Qualifications details are displayed correctly | As expected | Pass
|  | 3.1.10.3 | Add valid work experience | ESS-User is logged in | Company: ABC Ltd, Job Title: QA Engineer, From: 01/01/2020, To: 01/01/2022 | Navigate to My Info > Qualifications > Work Experience > Click Add > Fill all fields > Click Save | The work experience should be added sucessfully | As expected | Pass
|  | 3.1.10.4 | Add multiple work experiences | User has one existing entry | Company: XYZ Inc, Job Title: Tester | Navigate to My Info > Qualifications > Work Experience > Click Add > Fill all fields > Click Save | Both entries are listed under Work Experience | As expected | Pass
|  | 3.1.10.5 | Add experience with missing required field | ESS-User is logged in | Leave 'Job Title' empty | Navigate to My Info > Qualifications > Work Experience >Click Add > Leave Job Title blank > Click Save | Error message: 'Job Title is required' | As expected | Pass
|  | 3.1.10.6 | Add experience with future date | ESS-User is logged in | From Date: 01/01/2026 | Navigate to My Info > Qualifications > Work Experience >Click Add > Enter future date > Click Save | Validation error: 'Date cannot be in the future' | Date Addedd successfully | Fail
|  | 3.1.10.7 | Delete single work experience entry | At least one entry exists |  | Select one entry > Click Delete > Confirm | Selected entry is deleted and removed from list | As expected | Pass
|  | 3.1.10.8 | Delete multiple work experience entries | Multiple entries exist |  | Select multiple checkboxes > Click Delete > Confirm | All selected entries are removed | As expected | Pass
|  | 3.1.10.9 | Delete multiple work experience entries | Multiple entries exist |  | Select multiple checkboxes > Click Delete > Confirm | All selected entries are removed | As expected | Pass
|  | 3.1.10.10 | Verify comment section doesnt accept morre than 200 characters | ESS-User is logged in | comment : my current job is qa let it be more than 200 char | Navigate to My Info > Qualifications > Work Experience >Click Add > add comment | An error msg that tell the user about the chars limit | As expected | Pass
|  | 3.1.10.11 | Edit work experience entry | work experience entry |  | Navigate to My Info > Qualifications > Work Experience > Click edit entery | The work experience should be edited successfully | As expected | Pass
|  | 3.1.10.12 | Add valid education | ESS-User is logged in | Level : BSc, Institute:Birzeit , Year:2020 | Go to Education > Add > Fill all fields > Save | Entry is added to the list | As expected | Pass
|  | 3.1.10.13 | Save with missing requiered field | ESS-User is logged in |  | Go to Education > Add > Leave school blank > Save | Error: 'This feild is required' | As expected | Pass
|  | 3.1.10.14 | Delete education entry | At least one entry |  | Select entry > Click Delete | Entry is removed from the list | Doesnt Remove with msg that say the entery is not exist while its exsist | Fail
|  | 3.1.10.15 | Add a year using words instead of numbers | ESS-User is logged in | year : twenty twenty | Go to Education > Add > Year | Error : enter numbers | As expected | pass
|  | 3.1.10.16 | Add GPA/Score using words instead of numbers | ESS-User is logged in | year : twenty twenty | Go to Education > Add > Year | Error : enter numbers | Addedd successfully | Fail
|  | 3.1.10.17 | Add a new skill | ESS-User is logged in | Skill: Automation Testing | Go to Skills > Add > Fill skill > Save | Skill is added to the list | As expected | pass
|  | 3.1.10.18 | Add duplicate skill | Skill already exists | Skill: Automation Testing | Try adding same skill again | Duplicate entry error or allowed | As expected | pass
|  | 3.1.10.19 | Delete skill | At least one entry |  | Select skill > Click Delete | Skill is removed | As expected | pass
|  | 3.1.10.20 | Edit skill entry | skill entry |  | Navigate to My Info > Qualifications > Work Experience > Click edit entery | The skill should be edited successfully | As expected | pass
|  | 3.1.10.21 | Add new language with level | ESS-User is logged in | Language: English, Fluency: reading ,Competency:poor | Go to Languages > Add > Fill fields > Save | Language is listed | As expected | pass
|  | 3.1.10.22 | Add language without level | ESS-User is logged in | Language: English, Fluency: reading ,Competency:poor | Go to Languages > Add > Leave level empty > Save | Error: 'Level is required' | As expected | pass
|  | 3.1.10.23 | Delete language | At least one entry |  | Select language > Click Delete | Language entry is removed | As expected | pass
|  | 3.1.10.24 | Add a license entry | ESS-User is logged in | License: ISTQB, Date: 01/01/2021 | Go to Licenses > Add > Fill fields > Save | License is added to list | As expected | pass
|  | 3.1.10.25 | Add license with missing name | ESS-User is logged in | LicenseType : (empty) | Attempt to save license form | Error: 'License Name required' | As expected | pass
|  | 3.1.10.26 | Delete license | At least one entry |  | Select license > Click Delete | License is removed | As expected | pass
|  | 3.1.10.27 | Upload valid attachment | ESS-User is logged in | File: certificate.pdf (400KB) | Go to Attachments > Add > Upload file > Click Upload | File is listed under attachments | As expected | pass
|  | 3.1.10.28 | Upload file >1MB | ESS-User is logged in | File: largefile.pdf (1.5MB) | upload file >1MB | Error shown: 'File size exceeds limit' | As expected | pass
|  | 3.1.10.29 | Upload unsupported file type | ESS-User is logged in | File: script.exe | upload unsupported file | Error shown: 'Unsupported file type' | As expected | pass
|  | 3.1.10.30 | Delete uploaded attachment | Attachment exists | N/A | Select attachment > Click Delete | Attachment is removed | As expected | pass
3.1.11 | Membership | 3.1.11.1 | verify that the "Membership"button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | log in then Navigate to “My Info” → Look for Membership section | The Membership section should appear to the user | As expected | pass
|  | 3.1.11.2 | Verify visibility of Membership information | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “Membership ” | All Membership details are displayed correctly | As expected | pass
|  | 3.1.11.3 | Add a new membership entry | User logged in, on Membership page | Membership: ACCA Sub: 100 Currency: USD Start Date: 01/01/2024 | 1. Click “Add” 2. Enter all required data 3. Click “Save” | Membership is listed under membership table | As expected | pass
|  | 3.1.11.4 | Add multiple membership entries | User on Membership page | Membership:CIM,CIMA | Repeat steps above for each entry | All entries appear in the membership list | As expected | pass
|  | 3.1.11.5 | Submit form with missing required field | User on Add Membership form | Membership field left blank | 1. Click “Add” 2. Leave Membership field empty 3. Click “Save” | Validation error is displayed, This field is required | As expected | pass
|  | 3.1.11.6 | Upload a valid attachment | User on Add Membership form | File: cert.pdf | 1. Click “Add” under Attachment 2. Select valid file 3. Click “Upload” | File is uploaded and displayed under the entry | As expected | pass
|  | 3.1.11.7 | Upload an invalid file type | User on Add Membership form | File: file.exe | 1. Click “Add” under Attachment 2. Select invalid file 3. Click “Upload” | Upload fails, error message shown : file type not allowed | As expected | pass
|  | 3.1.11.8 | Delete a single membership entry | At least 1 membership entry exists | N/A | 1. Tick checkbox for one entry 2. Click “Delete” | Entry is deleted from the list | As expected | pass
|  | 3.1.11.9 | Delete multiple membership entries | Multiple entries exist | N/A | 1. Tick multiple checkboxes 2. Click “Delete” | Selected entries are deleted from the list | As expected | pass
|  | 3.1.11.10 | Verify file opens after upload | Attachment is uploaded | File: cert.pdf | 1. Click uploaded file 2. Verify it opens | File opens successfully | As expected | pass
|  | 3.1.11.11 | Cancel add membership | On Add Membership form | Fill some fields only | 1. Click “Add” 2. Enter partial info 3. Click “Cancel” | Form closes, no new membership is added | As expected | pass
|  | 3.1.11.12 | Validate numeric field format | On Add Membership form | Subscription amount: ABC | 1. Click “Add” 2. Enter letters in Subscription field 3. Click “Save” | Validation message: only numbers are allowed | As expected | pass
|  | 3.1.11.13 | Edit Membership entry | Membership entry |  | Navigate to My Info > Membership> Work Experience > Click edit entery | The Membership should be edited successfully | As expected | pass

## Test Cases (Admin)
Test Suite ID | Title | Test Case ID | Test Case Descriprion | Precondition | Test Data | Test Steps | Expected Result | Actual Result | Status | Notes
R3.2.1 | ADD USER | TC1 | Create user by admin and customize it as admin with valid data | Login as admin + Admin Page + Add User | User Role: Admin Employee Name Status: Enable Unique Username Password: Peter123 Password Confimation: Peter123 | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter valid inputs 5. Save | Add User as admin, New Admin can login | Cant create user, Because Employee Name is restricted by Lists (Type for Hints) | Fail | Fix: Employee Name must be selected from dropdown
|  | TC2 | Create user by admin and customize it as admin with valid data | Login as admin + Admin Page + Add User | User Role: Admin Choose Employee Name from hints Status: Enable Unique Username Password: Peter123 Password Confimation: Peter123 | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter valid inputs 5. Save | Add User as admin, New Admin can login | Add User as admin, New Admin can login | Pass
|  | TC3 | Create user by admin and customize it as ESS with valid data | Login as admin + Admin Page + Add User | User Role: ESS Choose Employee Name from hints Status: Enable Unique Username Password: Jacki123 Password Confimation: Jacki123 | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter valid inputs 5. Save | Add User as ESS, New ESS can login | Add User as ESS, New ESS can login | Pass
|  | TC4 | Create user by admin and customize it as admin/ESS with making it disabled | Login as admin + Admin Page + Add User | User Role: Admin/ESS Choose Employee Name from hints Status: Disable Unique Username Password: Hello1gg Password Confimation: Hello1gg | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter invalid inputs by making status disable 5. Save | Add User as admin/ESS, New user can't login | Add User as admin/ESS, New user can't login | Pass
|  | TC5 | Password Mismatch | Login as admin + Admin Page + Add User | User Role: Admin/Employee Choose Employee Name from hints Status: Enable Unique Username Password: Gaza1gg Password Confimation: aaaa1gg | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter invalid inputs 5. Save | Warning Message: "Passwords do not match" + No Save | Warning Message: "Passwords do not match" + No Save | Pass
|  | TC6 | Password Complexity | Login as admin + Admin Page + Add User | User Role: Admin/Employee Choose Employee Name from hints Status: Enable Unique Username Password: 123 Password Confimation: 123 | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter invalid inputs 5. Save | Warning Message: "Should have at least 7 characters" + No Save | Warning Message: "Should have at least 7 characters" + No Save | Pass
|  | TC7 | Duplicate Username | Login as admin + Admin Page + Add User | User Role: Admin/Employee Choose Employee Name from hints Status: Enable Duplicate Username Password: 123Jack Password Confimation: 123Jack | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter invalid inputs 5. Save | Warning Message: "Already Exists" + No Save | Warning Message: "Already Exists" + No Save | Pass
|  | TC8 | Missing Required Fields | Login as admin + Admin Page + Add User | Leave one field blank at a time | 1. Login as admin 2. Open admin page 3. Add Button 4. Empty input 5. Save | Warning Message: "Required Field" + No Save | Warning Message: "Required Field" + No Save | Pass | Test each field separately.
|  | TC9 | Long Username | Login as admin + Admin Page + Add User | User Role: Choose Employee Name from hints Status: Enable Username: JackJackJackJackJack Password: 123Jack Password Confimation: 123Jack | 1. Login as admin 2. Open admin page 3. Add Button 4. edge case 5. Save | Warning Message: "Should not exceed 40 characters" + No Save | Warning Message: "Should not exceed 40 characters" + No Save | Pass
|  | TC10 | Long Password | Login as admin + Admin Page + Add User | User Role: Admin/ESS Choose Employee Name from hints Status: Enable Username: user123 Password: 123Jack123Jack123Jack123Jack Password Confimation: 123Jack123Jack123Jack123Jack | 1. Login as admin 2. Open admin page 3. Add Button 4. edge case 5. Save | Warning Message: "Should not exceed 64 characters" + No Save | Warning Message: "Should not exceed 64 characters" + No Save | Pass
| DELETE USER | TC11 | Delete single Admin user | Login as admin + Admin Page + Delete User | Delete Admin User | 1. Login as admin 2. Open admin page 3. Delete Admin User | Admin user removed from list | Admin user removed from list | Pass
|  | TC12 | Delete single ESS user | Login as admin + Admin Page + Delete User | Delete ESS User | 1. Login as admin 2. Open admin page 3. Delete ESS User | ESS user removed from list | ESS user removed from list | Pass
|  | TC13 | Delete Admin & ESS users | Login as admin + Admin Page + Delete User | Delete Admin & ESS users | 1. Login as admin 2. Open admin page 3. Delete Admin & ESS users | Admin & ESS users removed from list | Admin & ESS users removed from list | Pass
|  | TC14 | Delete All | Login as admin + Admin Page + Delete User | Delete All | 1. Login as admin 2. Open admin page 3. Delete All | All removed from list except Current Admin | All removed from list except Current Admin | Pass
|  | TC15 | Delete with no selection | Login as admin + Admin Page + Delete User | Delete with no selection | 1. Login as admin 2. Open admin page 3. Delete with no selection | No Delete | No Delete | Pass
|  | TC16 | Delete user then Verify login blocked | Login as admin + Admin Page + Delete User | Username/Password of deleted user | Attempt login with deleted user credentials | Error: "Invalid credentials" or "Account not found" | Error: "Invalid credentials" or "Account not found" | Pass
|  | TC17 | Delete current admin (self) | Login as admin + Admin Page + Delete User | Delete current admin | 1. Login as admin 2. Open admin page 3. Delete current user | warning message: "Cant be deleted" | warning message: "Cant be deleted" | Pass
| EDIT USER | TC18 | Edit username (valid) | Login as admin + Admin Page + Edit User | New username: John_updated | 1. Login as admin 2. Open admin page 3. Edit User 4. username | username updated | username updated | Pass
|  | TC19 | Change role (Admin → ESS) | Login as admin + Admin Page + Edit User | Role: ESS | 1. Login as admin 2. Open admin page 3. Edit User 4. user role | role updated | role updated | Pass
|  | TC20 | Edit Employee Name | Login as admin + Admin Page + Edit User | Employee Name: John | 1. Login as admin 2. Open admin page 3. Edit User 4. employee name | Employee name changed | No records found (dropdown list) | Fail | Same Bug as TC1
|  | TC21 | Change the status of the employee | Login as admin + Admin Page + Edit User | status disabled | 1. Login as admin 2. Open admin page 3. Edit User 4. status | changed | changed | Pass
|  | TC22 | check the login of the disable employee | Login as admin + Admin Page + Edit User | status disabled | 1. Login as admin 2. Open admin page 3. Edit User 4. status | cant login Warning Message: "Account disabled " | cant login Warning Message: "Account disabled " | Pass
|  | TC23 | chage password | Login as admin + Admin Page + Edit User | New Pass: Test123 Confirm Pass: Test123 | 1. Login as admin 2. Open admin page 3. Edit User 4. password | password changed | password changed | Pass
|  | TC24 | Password mismatch | Login as admin + Admin Page + Edit User | New Pass: Test321 Confirm Pass: Murad123 | 1. Login as admin 2. Open admin page 3. Edit User 4. password | "Passwords do not match." No save. | "Passwords do not match." No save. | Pass
|  | TC25 | Duplicate username | Login as admin + Admin Page + Edit User | Username: Test _ Updated | 1. Login as admin 2. Open admin page 3. Edit User 4. username | username exist | username exist | Pass
|  | TC26 | Clear required field | Login as admin + Admin Page + Edit User | Leave one field blank at a time | 1. Login as admin 2. Open admin page 3. Edit User 4. left one blank empty | Warning Message: "Required Field" + No Save | Warning Message: "Required Field" + No Save | Pass
R3.2.2.1 | Add Job | TC27 | Add valid job title | Login as admin + (Job) Job Titles + Add | Job Title: Software Engineer Description: Develops applications | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Added Job | Added Job | Pass
|  | TC28 | Add job title without description/specification/note | Login as admin + (Job) Job Titles + Add | Job Title: QA Analyst | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Added Job | Added Job | Pass
|  | TC29 | Duplicate Job Title | Login as admin + (Job) Job Titles + Add | Job Title: Software Engineer | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Job Title exist | Job Title exist | Pass
|  | TC30 | Empty Field/s | Login as admin + (Job) Job Titles + Add | Blank field/s | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Field is required + No Save | Field is required + No Save | Pass
|  | TC31 | Add long job title more than 100 char | Login as admin + (Job) Job Titles + Add | More than 100 char in job title | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Should not exceed 100 characters | Should not exceed 100 characters | Pass
|  | TC32 | Special chars in job title | Login as admin + (Job) Job Titles + Add | A@@a | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Cant accept special chars | Added Job | Fail
|  | TC33 | Upload File | Login as admin + (Job) Job Titles + Add | Upload File | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | File Uploaded | File not uploaded | Fail
| Edit Job | TC34 | Edit job title | Login as admin + (Job) Job Titles + Edit | New Job Title: UX Designer New Description: User experience focus | 1. Login as admin 2. Open admin page 3. Job Title 4. Edit icon | Edited | Edited | Pass
|  | TC35 | Reply same test cases for Add | Login as admin + (Job) Job Titles + Edit | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. Edit icon | Edited | Edited | Fail | Same Bugs
| Delete Job | TC36 | Delete Job | Login as admin + (Job) Job Titles + Delete | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. delete icon | Deleted | Deleted | Pass
|  | TC37 | Delete 2 Jobs | Login as admin + (Job) Job Titles + Delete | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. delete icon | Deleted | Deleted | Pass
|  | TC38 | Delete All | Login as admin + (Job) Job Titles + Delete | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. delete icon | Deleted | Deleted | Pass
|  | TC39 | Delete no selection | Login as admin + (Job) Job Titles + Delete | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. delete icon | No Delete | No Delete | Pass
R3.2.2.2 | Add Pay Grade | TC40 | Add valid pay grade | Login as admin + (Job) Pay Grades + Add | P1 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Pay Grade added, Show currency form | Pay Grade added, Show currency form | Pass
|  | TC41 | Add currency to pay grade (valid) | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: 3000 Max Salary: 6000 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Currency added | Currency added | Pass
|  | TC42 | Max smaller than Min salary (invalid) | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: 6000 Max Salary: 3000 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Warnin Message | Warnin Message | Pass
|  | TC43 | Add multiple currencies | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: 3000 Max Salary: 6000 --- Currency: SAR Min Salary: 2000 Max Salary: 5000 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Added | Added | Pass
|  | TC44 | Negative salary values | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: -12 Max Salary: -1 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Warnin Message | Warnin Message | Pass
|  | TC45 | Duplicate currency in pay grade | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: 3000 Max Salary: 6000 --- Currency: USD Min Salary: 3000 Max Salary: 6000 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Not acceptable | Not acceptable | Pass
| Delete Pay Grade | TC46 | Delete single currency | Login as admin + (Job) Pay Grades + Delete | N/A | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Delete | Deleted | Deleted | Pass
|  | TC47 | delete all currencies | Login as admin + (Job) Pay Grades + Delete | N/A | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Delete | Deleted | Deleted | Pass
|  | TC48 | Delete entire pay grade | Login as admin + (Job) Pay Grades + Delete | N/A | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Delete | Deleted | Deleted | Pass
|  | TC49 | Delete all grades | Login as admin + (Job) Pay Grades + Delete | N/A | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Delete | Deleted | Deleted | Pass
| Edit Pay Grade | TC50 | Edit pay grade name P1 | Login as admin + (Job) Pay Grades + Edit | P100 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Edit Pay grade | updated | updated | Pass
|  | TC51 | Edit currency details | Login as admin + (Job) Pay Grades + Edit | New Min: 3500 New Max: 6500 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Edit Pay grade | updated | updated | Pass
R3.2.2.3 | Add Employment Status | TC52 | Add valid employment status | Login as admin + (Job) Employment Status + Add | Full-Time | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Added | Added | Pass
|  | TC53 | Add duplicate employment status | Login as admin + (Job) Employment Status + Add | Full-Time | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Warning Message Already exists | Warning Message Already exists | Pass
|  | TC54 | Add long status name more than 100 chars | Login as admin + (Job) Employment Status + Add | More than 100 char in status | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Warning Message Should not exceed 50 characters | Warning Message Should not exceed 50 characters | Pass
|  | TC55 | Special chars in status name | Login as admin + (Job) Employment Status + Add | Full@Time | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Warning Message Cant include special chars except "-" | Added | Fail
|  | TC56 | Add empty status | Login as admin + (Job) Employment Status + Add | Empty | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Required | Required | Pass
| Delete Employment Status | TC57 | Delete single status | Login as admin + (Job) Employment Status + Delete | N/A | 1. Login as admin 2. Open admin page 3. Employement Status 4. Delete | Deleted | Deleted | Pass
|  | TC58 | delete all statuses | Login as admin + (Job) Employment Status + Delete | N/A | 1. Login as admin 2. Open admin page 3. Employement Status 4. Delete | Deleted | Deleted | Pass
|  | TC59 | delete with no selection | Login as admin + (Job) Employment Status + Delete | N/A | 1. Login as admin 2. Open admin page 3. Employement Status 4. Delete | Not Deleted | Not Deleted | Pass
| Edit Employment Status | TC60 | Edit employment status | Login as admin + (Job) Employment Status + Edit | Edit from Fulltime to Full Time | 1. Login as admin 2. Open admin page 3. Employement Status 4. Edit | Edited | Edited | Pass
R3.2.2.4 | Add Job Categories | TC61 | Add valid job category | Login as admin + (Job) job category + Add | BackEnd | 1. Login as admin 2. Open admin page 3. job category 4. Add | Added | Added | Pass
|  | TC62 | Add duplicate job category | Login as admin + (Job) job category + Add | BackEnd | 1. Login as admin 2. Open admin page 3. job category 4. Add | Warning Message Already exists | Warning Message Already exists | Pass
|  | TC63 | Add long job name more than 100 chars | Login as admin + (Job) job category + Add | More than 100 char in status | 1. Login as admin 2. Open admin page 3. job category 4. Add | Warning Message Should not exceed 50 characters | Warning Message Should not exceed 50 characters | Pass
|  | TC64 | Special chars in job name | Login as admin + (Job) job category + Add | Data$$Analyst | 1. Login as admin 2. Open admin page 3. job category 4. Add | Warning Message Cant include special chars except "-" | Added | Fail | Same bug as TC55
|  | TC65 | Add empty status | Login as admin + (Job) job category + Add | Empty | 1. Login as admin 2. Open admin page 3. job category 4. Add | Required | Required | Pass
| Delete Job Categories | TC66 | Delete single job | Login as admin + (Job) job category + Delete | N/A | 1. Login as admin 2. Open admin page 3. job category 4. Delete | Deleted | Deleted | Pass
|  | TC67 | delete all job | Login as admin + (Job) job category + Delete | N/A | 1. Login as admin 2. Open admin page 3. job category 4. Delete | Deleted | Deleted | Pass
|  | TC68 | delete with no selection | Login as admin + (Job) job category + Delete | N/A | 1. Login as admin 2. Open admin page 3. job category 4. Delete | Not Deleted | Not Deleted | Pass
| Edit Job Categories | TC69 | Edit job title | Login as admin + (Job) job category + Edit | Edit from Backend to Back End | 1. Login as admin 2. Open admin page 3. job category 4. Edit | Edited | Edited | Pass
R3.2.2.5 | Add Work Shift | TC70 |  | Login as admin + (Job) Work Shift + Add | Shift Name: Morning Working Hours: 08:00 AM - 05:00 PM | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Added | Added | Pass
|  | TC71 | Add shift with missing required fields | Login as admin + (Job) Work Shift + Add | Shift Name: Evening Working Hours: Empty | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Required Field | Required Field | Pass
|  | TC72 | Assign employee to shift | Login as admin + (Job) Work Shift + Add | Shift Name: Evening Working Hours: 06:00 PM - 11:00 PM | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Added | Added | Pass
|  | TC73 | Add overlapping shift times | Login as admin + (Job) Work Shift + Add | Shift Name: Evening Working Hours: 11:00 PM - 07:00 PM | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Warning Message | Warning Message | Pass
|  | TC74 | Assign employee to multiple shifts | Login as admin + (Job) Work Shift + Add | Ranga Akunuri | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | employee name will not appear in other messages | employee name will not appear in other messages | Pass
| Edit Work Shift | TC75 | Edit shift details | Login as admin + (Job) Work Shift + Edit | Evenin to Evening Shift | 1. Login as admin 2. Open admin page 3. Work Category 4. Edit | Edited | Edited | Pass
|  | TC76 | Remove employee from shift | Login as admin + (Job) Work Shift + Add | N/A | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Removed | Removed | Pass
| Delete Work Shift | TC77 | Delete single shift | Login as admin + (Job) Work Shift + Delete | N/A | 1. Login as admin 2. Open admin page 3. Work Category 4. Delete | Deleted | Deleted | Pass
|  | TC78 | Delete All | Login as admin + (Job) Work Shift + Delete | N/A | 1. Login as admin 2. Open admin page 3. Work Category 4. Delete | Deleted | Deleted | Pass
|  | TC79 | delete with no selection | Login as admin + (Job) Work Shift + Delete | N/A | 1. Login as admin 2. Open admin page 3. Work Category 4. Delete | Cant Delete | Cant Delete | Pass
R3.2.3.1 | Edit General Information | TC80 | Edit general information with valid data | Login as admin + (Organization) General Information + Edit | Valid Inputs in all fields | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Edited | Edited | Pass
|  | TC81 | Edit with invalid email format | Login as admin + (Organization) General Information + Edit | Info@orangehrm.a | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warning Message | Accept the email | Fail
|  | TC82 | Edit with invalid phone format | Login as admin + (Organization) General Information + Edit | 132iugiug | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warning Message | Warning Message | Pass
|  | TC83 | Partial update of information | Login as admin + (Organization) General Information + Edit | invalid data | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Edited | Edited | Pass
|  | TC84 | Cancel editing without saving | Login as admin + (Organization) General Information + Edit | N/A | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Should not Eexcept, specially if there is a warning message | Accept Data | Pass
|  | TC85 | Verify field length limits | Login as admin + (Organization) General Information + Edit | Enter More than 100 char | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warnin message | Warnin message | Pass
|  | TC86 | Verify required fields | Login as admin + (Organization) General Information + Edit | Name is just required | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warnin message | Warnin message | Pass
|  | TC87 | Verify special characters in fields | Login as admin + (Organization) General Information + Edit | @@@ | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warning Message | Warning Message | Pass
|  | TC88 | Verify country dropdown list | Login as admin + (Organization) General Information + Edit | N/A | 1. Login as admin 2. Open admin page 3. General information 4. Edit | choosed from the list | choosed from the list | Pass
R3.2.3.2 |  | T1.1 | Admin successfully adds a new location | 1. Admin is logged in. 2. "Locations" page is accessible. | Name (Required) City Zip/Postal code phone address State/Province Country (Required) Fax Notes | 1. Navigate to Admin > Organization > Locations. 2. Click + Add. 3. Enter valid data. 4. Click Save. | New location is saved and appears in the list. | New location is saved and appears in the list. | Passed
|  | T1.2 | Admin edits an existing location | 1. At least one location exists. | Original City Updated City | 1. Select "Gaza Office". 2. Click Edit. 3. Update City field "Jersalum" . 4. Click Save. | Location details are updated in the list. | Location details are updated in the list. | Passed
|  | T1.3 | Admin deletes a location | 1. Location exists (Gaza Office). | the date of saved location | 1. Select the location. 2. Click Delete. 3. Confirm deletion. | Location is removed from the list. | Location is removed from the list. | Passed
|  | T1.4 | Admin searches for a location | 1. Multiple locations exist. | Search data: name or city or country | 1. Enter "Gaza office" in the search bar. 2. Click Search. | Only "Gaza Office" is displayed. | Only "Gaza Office" is displayed. | Passed
|  | T1.5 | Add location with missing mandatory fields | 1. Admin is logged in. | Name: (Blank) Country: (Blank) | 1. Click + Add. 2. Leave Name/Country blank. 3. Click Save. | Error message appears, not saved. | Error message appears, not saved. | Passed
|  | T1.6 | Edit location with invalid phone format | 1. Location exists. | Phone: 123-ABC-4567 | 1. Edit the location. 2. Enter invalid phone. 3. Click Save. | Error prompts for valid phone format , not saved. | Error prompts for valid phone format , not saved. | Passed
|  | T1.7 | Delete a location with assigned employees | 1. Location has employees | information of location with employess | 1. Attempt to delete the location. | System prevents deletion (warning message). | the system delete the location without warning message | Failed
|  | T1.8 | Add location with more maximum field length | 1. Admin is logged in. | Name: A.repeat(255) City: B.repeat(100) | 1. Enter max-length data. 2. Click Save. | Record is not saved | the system doesn't accpet the records and the warning messages appear | Passed
|  | T1.9 | Search with special characters | 1. Locations exist. | Search Term: @#$% | 1. Enter special characters. 2. Click Search. | No results | No results | Passed
|  | T1.10 | Edit country to a non-listed value | 1. Location exists. | Country: Mars | 1. Attempt to edit Country to an invalid value. | Dropdown restricts to valid countries. | Dropdown restricts to valid countries. | Passed
Structure feature
R3.2.3.3 |  | T2.1 | Admin adds a new unit under parent company | 1. Admin is logged in. 2. "Structure" page is accessible. 3. edit option is enable | Unit ID ,Unit Name ,Description | 1. Navigate to Admin > Organization > Structure. 2. Click Edit then Add. 3. Enter valid data. 4. Click Save. | New unit appears under the parent company (OrangeHRM). | New unit appears under the parent company (OrangeHRM). | Passed
|  | T2.2 | Admin adds a sub-unit under an existing unit | 1. Unit exists (e.g., Administration). | Sub-unit Name: HR Team Description: Recruitment and employee management | 1. Click [+] next to Administration. 2. Click Add. 3. Enter valid data. 4. Click Save. | Sub-unit appears under Administration in the hierarchy. | Sub-unit appears under Administration in the hierarchy. | Passed
|  | T2.3 | Admin edits a unit’s details | 1. Unit exists (e.g., Engineering). | Updated Name: R&D Engineering | 1. Select Engineering. 2. Click Edit. 3. Update name. 4. Click Save. | Unit details are updated in the structure. | Unit details are updated in the structure. | Passed
|  | T2.4 | Admin deletes a unit | 1. Unit exists (e.g., Client Services). | Unit Name: Client Services | 1. Click Delete next to the unit. 2. Confirm deletion. | Unit is removed from the structure. | Unit is removed from the structure. | Passed
|  | T2.5 | Admin collapses/expands units | 1. Units with sub-units exist. | ---- | 1. Click Collapse (˅) next to a unit. 2. Click Expand (>). | Sub-units are hidden/shown as expected. | Sub-units are hidden/shown as expected. | Passed
|  | T2.6 | Add unit with missing mandatory fields | 1. Admin is logged in. | Unit Name: (Blank) | 1. Click Add. 2. Leave Name blank. 3. Click Save. | Error message appears; unit not saved. | Error message appears; unit not saved. | Passed
|  | T2.7 | Delete a unit with sub-units | 1. Unit has sub-units (e.g., Administration). | Unit Name: Administration | 1. Attempt to delete the unit. | System prevents deletion (warning message). | the system delete the unit with no warning message | Failed
|  | T2.8 | Edit unit with invalid characters | 1. Unit exists. | Unit Name: Finance@#$ | 1. Edit unit. 2. Enter invalid name. 3. Click Save. | Error prompts for valid input. | the system accept the name | Failed
|  | T2.9 | Add unit with more maximum field length | 1. Admin is logged in. | Unit Name: A.repeat(255) Description: B.repeat(500) | 1. Enter max-length data. 2. Click Save. | Unit is not saved | the system doesn't accpet the edit | Passed
|  | T2.10 | Add multiple nested sub-units (5+ levels) | 1. Parent unit exists. | Sub-unit Names: Level 1, Level 2, ..., Level 5 | 1. Add sub-units recursively under each level. | Hierarchy is displayed correctly without UI breaks. | Hierarchy is displayed correctly without UI breaks. | Passed
|  | T2.11 | Search for a unit with special characters | 1. Units exist. | Search Term: @Engineering | 1. Enter special characters in search. | System handles input gracefully (no errors). | System handles input gracefully (no errors). | Passed
Skills feature
R3.2.4.1 |  | T3.1 | Admin adds a new skill | 1. Admin is logged in. 2. "Skills" page is accessible. | Name: Project Management Description: Agile and Scrum methodologies | 1. Navigate to Admin > Qualifications > Skills. 2. Click + Add. 3. Enter valid data. 4. Click Save. | New skill appears in the skills list. | New skill appears in the skills list. | Passed
|  | T3.2 | Admin edits an existing skill | 1. Skill exists (e.g., Content Creation). | Updated Description: Digital Marketing Skill | 1. Click Edit next to the skill. 2. Update description. 3. Click Save. | Skill details are updated in the list. | Skill details are updated in the list. | Passed
|  | T3.3 | Admin deletes a single skill | 1. Skill exists (e.g., G Suite). | Name: G Suite | 1. Click Delete next to the skill. 2. Confirm deletion. | Skill is removed from the list. | Skill is removed from the list. | Passed
|  | T3.4 | Admin deletes multiple skills | 1. Multiple skills exist. | Selected Skills: Content Creation, G Suite | 1. Check skills to delete. 2. Click Delete Selected. 3. Confirm deletion. | Selected skills are removed. | Selected skills are removed. | Passed
|  | T3.5 | Admin views all skills | 1. Skills exist in the system. | --- | 1. Navigate to Skills page. | All skills are displayed in a paginated list. | All skills are displayed in a paginated list. | Passed
|  | T3.6 | Add skill with missing mandatory field (Name) | 1. Admin is logged in. | Name: (Blank) Description: Valid description | 1. Click + Add. 2. Leave Name blank. 3. Click Save. | Error message appears; skill not saved. | Error message appears; skill not saved. | Passed
|  | T3.7 | Edit skill with invalid data (special characters) | 1. Skill exists. | Name: Python#@! | 1. Edit skill. 2. Enter invalid name. 3. Click Save. | Error prompts for valid input. | the system accept the edit | Failed
|  | T3.8 | Add skill with more than maximum field length | 1. Admin is logged in. | Name: A.repeat(255) Description: B.repeat(500) | 1. Enter max-length data. 2. Click Save. | Skill is not saved . | the system doesn't save the skill | Passed
|  | T3.9 | Bulk delete all skills | 1. Multiple skills exist. | Select All: True | 1. Select all skills. 2. Click Delete Selected. 3. Confirm deletion. | All skills are removed | All skills are removed | Passed
Education feature
R3.2.4.2 |  | T4.1 | Admin adds a new education level | 1. Admin is logged in. 2. "Education" page is accessible. | Level: Doctorate | 1. Navigate to Admin > Qualifications > Education. 2. Click + Add. 3. Enter valid data. 4. Click Save. | New education level appears in the list. | New education level appears in the list. | Passed
|  | T4.2 | Admin edits an existing education level | 1. Education level exists (e.g., Bachelor’s Degree). | Updated Level: Bachelor of Science | 1. Click Edit next to the education level. 2. Update the field. 3. Click Save. | Education level is updated in the list. | Education level is updated in the list. | Passed
|  | T4.3 | Admin deletes a single education level | 1. Education level exists (e.g., College Undergraduate). | Level: College Undergraduate | 1. Click Delete next to the education level. 2. Confirm deletion. | Education level is removed from the list. | Education level is removed from the list. | Passed
|  | T4.4 | Admin deletes multiple education levels | 1. Multiple education levels exist. | Selected Levels: High School Diploma, Master’s Degree | 1. Check levels to delete. 2. Click Delete Selected. 3. Confirm deletion. | Selected levels are removed. | Selected levels are removed. | Passed
|  | T4.5 | Admin views all education levels | 1. Education levels exist in the system. | ---- | 1. Navigate to Education page. | All levels are displayed in a paginated list. | All levels are displayed in a paginated list. | Passed
|  | T4.6 | Add education level with missing mandatory field | 1. Admin is logged in. | Level: (Blank) | 1. Click + Add. 2. Leave Level blank. 3. Click Save. | Error message appears; record not saved. | Error message appears; record not saved. | Passed
|  | T4.7 | Edit education level with invalid data (special characters) | 1. Education level exists. | Level: PhD@#$ | 1. Edit the level. 2. Enter invalid data. 3. Click Save. | Error prompts for valid input. | the system accept the name | Failed
|  | T4.8 | Add education level with more than maximum field length | 1. Admin is logged in. | Level: A.repeat(255) | 1. Enter max-length data. 2. Click Save. | Education level is not saved | the system doen't accept and not saved | Passed
|  | T4.9 | Add duplicate education level | 1. Education level exists (e.g., High School Diploma). | Level: High School Diploma | 1. Attempt to add the same level again. | System prevents duplication (error message). | System prevents duplication (error message). | Passed
|  | T4.10 | Bulk delete all education levels | 1. Multiple education levels exist. | Select All: True | 1. Select all levels. 2. Click Delete Selected. 3. Confirm deletion. | All levels are removed | All levels are removed | Passed
License feature
R3.2.4.3 |  | T5.1 | Admin adds a new license | 1. Admin logged in 2. Licenses page accessible | Name: AWS Certified Solutions Architect | 1. Navigate to Admin > Qualifications > Licenses 2. Click +Add 3. Enter name 4. Click Save | New license appears in licenses list | New license appears in licenses list | Passed
|  | T5.2 | Admin edits existing license | 1. License exists (e.g., CDMP) | Updated Name: Certified Digital Marketing Pro | 1. Click Edit next to license 2. Update name 3. Click Save | License details updated in list | License details updated in list | Passed
|  | T5.3 | Admin deletes single license | 1. License exists (e.g., CCNA) | Name: Cisco Certified Network Associate | 1. Click Delete next to license 2. Confirm deletion | License removed from list | License removed from list | Passed
|  | T5.4 | Admin deletes multiple licenses | 1. Multiple licenses exist | Selected: CISM, MCSE | 1. Check licenses to delete 2. Click Delete Selected 3. Confirm | Selected licenses removed | Selected licenses removed | Passed
|  | T5.5 | Admin views all licenses | 1. Licenses exist in system | ----- | 1. Navigate to Licenses page | All licenses displayed in paginated list | All licenses displayed in paginated list | Passed
|  | T5.6 | Add license with missing name | 1. Admin logged in | Name: (Blank) | 1. Click +Add 2. Leave name blank 3. Click Save | Error appears; license not saved | Error appears; license not saved | Passed
|  | T5.7 | Edit license with invalid characters | 1. License exists | Name: PMI@ACP! | 1. Edit license 2. Enter invalid name 3. Click Save | Error prompts for valid input | the system accept the name | Failed
|  | T5.8 | Add license with more than max length name | 1. Admin logged in | Name: A.repeat(255) | 1. Enter max-length name 2. Click Save | License not saved | the system doesn't accept the name and not saved | Passed
|  | T5.9 | Add duplicate license name | 1. License exists (MCSE) | Name: Microsoft Certified Systems Engineer | 1. Attempt to add same name | System prevents duplication | System prevents duplication | Passed
|  | T5.10 | Bulk delete all licenses | 1. Multiple licenses exist | Select All: True | 1. Select all 2. Delete Selected 3. Confirm | All licenses removed | All licenses removed | Passed
Languages feature
R3.2.4.4 |  | T6.1 | Admin adds a new language | 1. Admin logged in 2. Languages page accessible | Name: German | 1. Navigate to Admin > Qualifications > Languages 2. Click +Add 3. Enter name 4. Click Save | New language appears in list | New language appears in list | Passed
|  | T6.2 | Admin edits existing language | 1. Language exists (e.g., Chinese) | Updated Name: Mandarin | 1. Click Edit next to language 2. Update name 3. Click Save | Language details updated | Language details updated | Passed
|  | T6.3 | Admin deletes single language | 1. Language exists (e.g., Arabic) | Name: Arabic | 1. Click Delete next to language 2. Confirm deletion | Language removed from list | Language removed from list | Passed
|  | T6.4 | Admin deletes multiple languages | 1. Multiple languages exist | Selected: French, Russian | 1. Check languages to delete 2. Click Delete Selected 3. Confirm | Selected languages removed | Selected languages removed | Passed
|  | T6.5 | Admin views all languages | 1. Languages exist in system | ---- | 1. Navigate to Languages page | All languages displayed | All languages displayed | Passed
|  | T6.6 | Add language with missing name | 1. Admin logged in | Name: (Blank) | 1. Click +Add 2. Leave name blank 3. Click Save | Error appears; not saved | Error appears; not saved | Passed
|  | T6.7 | Edit language with invalid characters | 1. Language exists | Name: Engl!sh@ | 1. Edit language 2. Enter invalid name 3. Click Save | Error prompts for valid input | the system accept the name | Failed
|  | T6.8 | Add language with more than max length name | 1. Admin logged in | Name: A.repeat(255) | 1. Enter max-length name 2. Click Save | Language not saved | the system doesn't accept the repeatation | Passed
|  | T6.9 | Add duplicate language | 1. Language exists (Spanish) | Name: Spanish | 1. Attempt to add same name | System prevents duplication | System prevents duplication | Passed
|  | T6.10 | Bulk delete all languages | 1. Multiple languages exist | Select All: True | 1. Select all 2. Delete Selected 3. Confirm | All languages removed | All languages removed | Passed
Memberships feature
R3.2.4.5 |  | T7.1 | Admin adds new membership | 1. Admin logged in 2. Memberships accessible | Name: PMP | 1. Navigate to Admin > Qualifications > Memberships 2. Click +Add 3. Enter name 4. Click Save | New membership appears in list | New membership appears in list | Passed
|  | T7.2 | Admin edits existing membership | 1. Membership exists (ACCA) | Updated Name: ACCA Global | 1. Click Edit next to membership 2. Update name 3. Click Save | Membership details updated | Membership details updated | Passed
|  | T7.3 | Admin deletes single membership | 1. Membership exists (CIM) | Name: Chartered Institute of Marketing | 1. Click Delete next to membership 2. Confirm deletion | Membership removed from list | Membership removed from list | Passed
|  | T7.4 | Admin deletes multiple memberships | 1. Multiple memberships exist | Selected: BCS, CIMA | 1. Check memberships to delete 2. Click Delete Selected 3. Confirm | Selected memberships removed | Selected memberships removed | Passed
|  | T7.5 | Admin views all memberships | 1. Memberships exist | ---- | 1. Navigate to Memberships page | All memberships displayed | All memberships displayed | Passed
|  | T7.6 | Add membership with blank name | 1. Admin logged in | Name: (Blank) | 1. Click +Add 2. Leave name blank 3. Click Save | Error appears; not saved | Error appears; not saved | Passed
|  | T7.7 | Edit membership with invalid characters | 1. Membership exists | Name: CIM@2025! | 1. Edit membership 2. Enter invalid name 3. Click Save | Error prompts for valid input | the system accept the name | Failed
|  | T7.8 | Add membership with more than max length name | 1. Admin logged in | Name: A.repeat(255) | 1. Enter max-length name 2. Click Save | Membership not saved | the system doesn't accept the repeatation | Passed
|  | T7.9 | Add duplicate membership | 1. Membership exists (BCS) | Name: British Computer Society | 1. Attempt to add same name | System prevents duplication | System prevents duplication | Passed
|  | T7.10 | Bulk delete all memberships | 1. Multiple memberships exist | Select All: True | 1. Select all 2. Delete Selected 3. Confirm | All memberships removed | All memberships removed | Passed

## Bug Reports (Employee)
Employee
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
BUG_3.1.10.6 | Add Work Experience with Future Date | System accepts future date without validation | Browser: Chrome Windows 11 Laptop-Asus | Medium | Major | 1. Go to My Info > Qualifications > Work Experience 2. Click "Add" 3. Set From Date to 01/01/2026 4. Click "Save" | Validation error: "Date cannot be in the future" | Entry is added successfully without validation error | Data inconsistency
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
BUG_3.1.10.14 | Delete Education Entry Fails | Existing education entry cannot be deleted | Browser: Chrome Windows 11 Laptop-Asus | High | Major | 1. Go to Education section 2. Select an existing entry 3. Click "Delete" | Entry is deleted successfully from the list | Error message: "Entry does not exist" appears even though the entry exists | Functional
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
BUG_3.1.10.16 | GPA/Score accepts alphabetic input | System allows non-numeric GPA input | Browser: Chrome Windows 11 Laptop-Asus | Medium | Moderate | 1. Go to My Info > Qualifications > Education 2. Click "Add" 3. Enter "twenty twenty" as Year 4. Click "Save" | Validation error: "Enter numbers only" | Entry is saved successfully with alphabetic characters | Input validation missing
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
BUG_3.0.1.1 | Account Lockout Not Triggered After Multiple Failed Login Attempts | The system allows repeated failed login attempts without locking the account or displaying a security warning | Browser: Edge Windows 11 Laptop-Asus | High | Moderate | 1. Enter wrong password multiple times 2. Observe system behavior | System should lock account or display warning | No action was taken | This issue may pose a potential security risk | #VALUE!
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof | Priority | Seviority
BUG_3.0.1.2 | Using browser back after login | After login the user click back, thin the system back to login page without log out | Browser: Chrome Windows 11 Laptop-Asus | Low | Major | 1. Log in with valid credintals 2. click on browser back | System should not return to login page unless logged out | Login page reappeared but was unresponsive |  | #VALUE! | Low | Minor
[11 empty] | Medium | Moderate
[11 empty] | High | Major
[11 empty] | Immediate | Critical
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
BUG_3.1.3.3 | The system accept invalid mobile | In the "contact details" the system accept "5" as a phone number | Browser: Edge Windows 11 Laptop-Asus | Medium | Moderate | 1. Access 'My Info' > 'Contact Details' 2. Enter invalid phone format 3. Click 'Save' | System should reject input | invalid phone accepted |  | #VALUE!
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
BUG_3.1.6.2 | Number Field Allows Alphabetic Characters in Immigration Section | In the "Immigration" the system accepts alphabetic input "ABD345"in the Number field, which is expected to allow numeric values only, as specified in the SRS document. | Browser: Edge Windows 11 Laptop-Asus | Medium | Moderate | 1. Go to 'Immigration' 2. Click 'Add' 3. Enter letters in Number field 4. Click 'Save' | System should reject it and display error message | Letters accepted in Number field |  | #VALUE!
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
BUG_3.1.3.11 | State field not showing dropdown (US) | When selecting "United States", the State field stays as text input instead of showing a dropdown list. | Browser: Edge Windows 11 Laptop-Asus | Medium | Moderate | 1. Access 'My Info' > 'Contact Details' 2. Select country = US | State field should become dropdown with US states list | Field remains manual input for all countries |  | #VALUE!
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
BUG_3.1.6.14 | "Issued Date" accepts future dates | In Immigration, the system accepts future dates in the "Issued Date" field without validation | Browser: Edge Windows 11 Laptop-Asus | High | Moderate | 1. Go to My Info > Immigration 2. Enter a future Issued Date | System should reject future dates with error message | Future date accepted with no validation |  | #VALUE!

## Bug Reports (Admin)
Admin
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof | Priority | Seviority
B1 | Employee Name Drop down list | Cant create employee name when adding user, because employee name is restricted by dropdown lists (You need type for hints) | Platform: Lenovo Laptop Browser: Brave OS: Windows 10 | Immediate | Moderate | 1. Login as admin 2. Open admin module 3. Add button 4. Employee Name | Text lable | Drop down list lable | Repeated in TC1, TC20 |  | Low | Minor
[11 empty] | Medium | Moderate
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof | High | Major
B2 | Accept special characters in job title | When enter special characters in Job title, label accepts it. | Platform: Lenovo Laptop Browser: Brave OS: Windows 10 | Low | Minor | 1. Login as admin 2. Open job module 3. add/edit job 4. job title | Warning Message: "Cant use characters in Username" + No Save | Label Accept the username | Repeated in TC32, TC35 |  | Immediate | Critical
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B3 | Special chars in Employment Status name | Can include any special chars in Employment Status | Platform: Lenovo Laptop Browser: Brave OS: Windows 10 | Low | Minor | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add/Edit 5. name | Warning Message Cant include special chars except "-" | Accepted | - For Example: Fullt@@TIME - Repeated in TC55, TC 64
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B4 | Delete a location with assigned employees | the system allows the deleation of the company have employess without any warning | Platform: HP Laptop Browser: Chrome OS: Windows 10 | Medium | Moderate | 1. Login as admin 2. Open admin page 3. Organization then locations 4. select company with employess 5. delete | warning message before delete | the system delete the company with employess without any warning message | Repeated in TC 1.7 | https://www.awesomescreenshot.com/video/41419138?key=21ff22e3f884c0373bf0bd1bbb741a47
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B5 | Delete a unit with sub-units | the system allows the deleation of the units contain sub units without any warning message | Platform: HP Laptop Browser: Chrome OS: Windows 10 | High | Moderate | 1. Navigate to Admin > Organization > Structure. 2. Click Edit then the system shows the units. 3. delete unit contain sub units | warning message before delete | the system delete the unit with sub units without any warning message | Repeated in TC 2.7 | https://www.awesomescreenshot.com/video/41419119?key=ee8ffcf0963b26fc9d6289283c13c24f
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B6 | the system accept the invalid characters in operations like add , edit and search in (locations,Structure , Education, Memberships, Lisences and Languges ) Features | the system accpet the fileds with special charactares without any prevention | Platform: HP Laptop Browser: Chrome OS: Windows 10 | Medium | Moderate | 1. Navigate to Admin > the feature . 2. Click Edit, add or search 3. Enter special characters in search bar or required field in add or edit operation . | the system must prevention having spiecal characters in required fildes | the system accept having spiecal characters in required fildes | Repeated in 2.8 , 3.7 , 4.7, 5.7, 6.7, 7.7

## RTM (Employee)
Requirement Traceability Matrix (RTM)
Req ID | Requirement Name | Reuirement Description | Test Case ID | Assigned To | Current Status
"3.0 | Login | ESS-User can log in with a valid username and password provided by the HR Admin | 3.0.1, 3.0.2, 3.0.3, 3.0.4, 3.0.5, 3.0.6, 3.0.7, 3.0.8, 3.0.9, 3.0.10, 3.0.11, 3.0.12, 3.0.13 | Mohammad Foqahaa | Complete
3.1.1 | Personal Details | The ESS-User can add/edit their personal information details. | 3.1.1.1, 3.1.1.2, 3.1.1.3, 3.1.1.4, 3.1.1.5, 3.1.1.6, 3.1.1.7, 3.1.1.8, 3.1.1.9, 3.1.1.10, 3.1.1.11, 3.1.1.12, 3.1.1.13, 3.1.1.14, 3.1.1.15, 3.1.1.16 |  |  | Statuses:
3.1.2 | Photograph | The ESS-User can add/edit their profile photo. | 3.1.2.1, 3.1.2.2, 3.1.2.3, 3.1.2.4 |  |  | Not Started
3.1.3 | Contact Details | The ESS-User can add/edit their Contact Details. | 3.1.3.1, 3.1.3.2, 3.1.3.3, 3.1.3.4, 3.1.3.5, 3.1.3.6, 3.1.3.7, 3.1.3.8, 3.1.3.9, 3.1.3.10, 3.1.3.11, 3.1.3.12 |  |  | Elaboration
3.1.4 | Emergency Contact | The ESS-User can add/delete their Emergency Contact details and upload supporting documents. | 3.1.4.1, 3.1.4.2, 3.1.4.3, 3.1.4.4, 3.1.4.5, 3.1.4.6, 3.1.4.7, 3.1.4.8, 3.1.4.9, 3.1.4.10, 3.1.4.11, 3.1.4.12, 3.1.4.13, 3.1.4.14 |  |  | Development
3.1.5 | Dependents | The ESS-User can add/delete their Dependents details and upload supporting documents. | 3.1.5.1, 3.1.5.2, 3.1.5.3, 3.1.5.4, 3.1.5.5, 3.1.5.6, 3.1.5.7, 3.1.5.8, 3.1.5.9, 3.1.5.10, 3.1.5.11, 3.1.5.12, 3.1.5.13, 3.1.5.14, 3.1.5.15 |  |  | Testing
3.1.6 | Immigration | The ESS-User can add/delete their Immigration details and upload supporting documents. | 3.1.6.1, 3.1.6.2, 3.1.6.3, 3.1.6.4, 3.1.6.5, 3.1.6.6, 3.1.6.7, 3.1.6.8, 3.1.6.9, 3.1.6.10, 3.1.6.11, 3.1.6.12, 3.1.6.13, 3.1.6.14, 3.1.6.15 |  |  | Complete
3.1.7 | Job Details | The ESS-User has to be able to view job details, So that he can see important employment information without being able to change it. | 3.1.7.1, 3.1.7.2, 3.1.7.3, 3.1.7.4, 3.1.7.5 | Nagham Taweel | Complete
3.1.8 | Salary | The salary details section of the ESS-User, has to be completely hidden , So that confidential salary information is protected and only accessible by the HR Admin. | 3.1.8.1, 3.1.8.2, 3.1.8.3, 3.1.8.4
3.1.9 | Report To | The ESS-User, has to be able to view the list of assigned supervisors (and subordinates if he's a supervisor). | 3.1.9.1, 3.1.9.2, 3.1.9.3, 3.1.9.4
3.1.10 | Qualifications | The ESS-User, can manage (add, update, and delete) his qualifications — including Work Experience, Education, Skills, Languages, Licenses, and Attachments. | 3.1.10.1, 3.1.10.2, 3.1.10.3, 3.1.10.4, 3.1.10.5, 3.1.10.6, 3.1.10.7, 3.1.10.8, 3.1.10.9, 3.1.10.10, 3.1.10.11, 3.1.10.12, 3.1.10.13, 3.1.10.14, 3.1.10.15, 3.1.10.16, 3.1.10.17, 3.1.10.18, 3.1.10.19, 3.1.10.20, 3.1.10.21, 3.1.10.22, 3.1.10.23, 3.1.10.24, 3.1.10.25, 3.1.10.26, 3.1.10.27, 3.1.10.28, 3.1.10.29, 3.1.10.30
3.1.11 | Membership | The ESS-User, can add, update, and delete his membership details and upload supporting attachments. | 3.1.11.1, 3.1.11.2, 3.1.11.3, 3.1.11.4, 3.1.11.5, 3.1.11.6, 3.1.11.7, 3.1.11.8, 3.1.11.9, 3.1.11.10, 3.1.11.11, 3.1.11.12, 3.1.11.13

## RTM (Admin)
Requirement Traceability Matrix (RTM)
Req ID | Requirement Name | Reuirement Description | Test Case ID | Assigned To | Current Status
R3.2.1 | User Management Module | Admin create user accounts with roles (Admin/ESS), and can edit or delete user accounts. | TC1, TC2, TC3, TC4, TC5, TC6, TC7, TC8, TC9, TC10, TC11, TC12, TC13, TC14, TC15, TC16, TC17, TC18, TC19, TC20, TC21, TC22, TC23, TC24, TC25, TC26 | Abdelrahman Murad | Complete
R3.2.2.1 | Job Titles | Admin can add/edit/delete job titles | TC27, TC28, TC29, TC30, TC31, TC32, TC33, TC34, TC35, TC36, TC37, TC38, TC39 |  |  | Statuses:
R3.2.2.2 | Pay Grades | Admin can add/edit/delete pay grades with identifying salary ranges. | TC40, TC41, TC42, TC43, TC44, TC45, TC46, TC47, TC48, TC49, TC50, TC51 |  |  | Not Started
R3.2.2.3 | Employment Status | Admin can add/edit/delete employment status. | TC52, TC53, TC54, TC55, TC56, TC57, TC58, TC59, TC60 |  |  | Elaboration
R3.2.2.4 | Job Categories | Admin can create/edit/delete job categories. | TC61, TC62, TC63, TC64, TC65, TC66, TC67, TC68, TC69 |  |  | Development
R3.2.2.5 | Work Shifts | Admin can assign work shirts for employees. | TC70, TC71, TC72, TC73, TC74, TC75, TC76, TC77, TC78, TC79 |  |  | Testing
R3.2.3.1 | General Information | Admin can edit companies general information. | TC80, TC81, TC82, TC83, TC84, TC85, TC86, TC87, TC88 |  |  | Complete
R3.2.3.2 | Locations | the admin control the Locations feature and perform opreations related to it like (search, add , edit , delete , view ) | TC (1.1, 1.2 , 1.3, 1.4 , 1.5 , 1.6 , 1.7 , 1.8 , 1.9 , 1.11 ) | Haya | Complete
R3.2.3.3 | Structure | the admin control the Structure feature and perform opreations related to the units and sub units like (search, expand, collapes, add , edit , delete , view ) | TC (2.1, 2.2 , 2.3, 2.4 , 2.5 , 2.6 , 2.7 , 2.8 , 2.9 , 2.11 , 2.12)
R3.2.4.1 | Skills | the admin control the skills feature and perform opreations related to it like ( add , edit , delete , view ) | TC (3.1, 3.2 , 3.3, 3.4 , 3.5 , 3.6 ,3.7 , 3.8 , 3.9 , 3.11 )
R3.2.4.2 | Education | the admin control the Education feature and perform opreations related to it like ( add , edit , delete , view ) | TC (4.1, 4.2 , 4.3, 4.4 , 4.5 , 4.6 ,4.7 , 4.8 ,4.9 , 4.11 )
R3.2.4.3 | License | the admin control the License feature and perform opreations related to it like add , edit , delete , view ) | TC (5.1, 5.2 , 5.3, 5.4 , 5.5 , 5.6 ,5.7 , 5.8 ,5.9 , 5.11 )
R3.2.4.4 | Languages | the admin control the Languages feature and perform opreations related to it like (, add , edit , delete , view ) | TC (6.1,6.2 , 6.3, 6.4 , 6.5 ,6.6 ,6.7 , 6.8 ,6.9 , 6.11 )
R3.2.4.5 | Memberships | the admin control the Memberships feature and perform opreations related to it like (add , edit , delete , view ) | TC (7.1,7.2 , 7.3, 7.4 , 7.5 ,7.6 ,7.7 , 7.8 ,7.9 , 7.11 )

## Test Summary Report
Test Report
Test Cycle | System Test
Executed | Passed |  |  |  | 287
| Failed |  |  |  | 15
| Total Tests Executed (Passed + Failed) |  |  |  |  | 302 | Total Tc's | 302
Pending | [5 empty] | 0 | Passed | 287
In Progress | [5 empty] | 0 | Failed | 15 | Total TCs | 305
Blocked | [5 empty] | 1 | Blocked | 1 | Passed | 288
(Sub-Total) Test Planed | [5 empty] | 302 |  |  | Failed | 16
[Pending - In Progress - Blocked - Test Executed] | [8 empty] | Blocked | 1
Functions (Test Scenarios) | Description | TCs Excuted % | TCs Passed % | TCs pending | Priority | Remarks
Login | ESS-User can log in with a valid username and password provided by the HR Admin | 100% | 85% | 0% | High
Personal Details | The ESS-User can add/edit their personal information details. | 100% | 100% | 0% | High
Photograph | The ESS-User can add/edit their profile photo. | 100% | 100% | 0% | Low
Contact Details | The ESS-User can add/edit their Contact Details. | 100% | 92% | 0% | High
Emergency Contact | The ESS-User can add/delete their Emergency Contact details and upload supporting documents. | 100% | 100% | 0% | High
Dependents | The ESS-User can add/delete their Dependents details and upload supporting documents. | 100% | 100% | 0% | Medium
Immigration | The ESS-User can add/delete their Immigration details and upload supporting documents. | 100% | 93% | 0% | Medium
Job Details | The ESS-User is able to view job details, without being able to change it. | 100% | 100% | 0% | High
Salary | The salary details section of the ESS-User is completely hidden So that , salary information is protected and only accessible by the HR Admin. | 100% | 75% | 0% | High
Report To | The ESS-User, is able to view the list of assigned supervisors (and subordinates if he's a supervisor). | 100% | 100% | 0% | Medium
Qualifications | The ESS-User, can manage (add, update, and delete) his qualifications — including Work Experience, Education, Skills, Languages, Licenses, and Attachments. | 100% | 90% | 0% | High
Membership | The ESS-User, can add, update, and delete his membership details and upload supporting attachments. | 100% | 100% | 0% | Low
User Management Module | Admin create user accounts with roles (Admin/ESS), and can edit or delete user accounts. | 100% | 92% | 0% | High
Job Titles | Admin can add/edit/delete job titles | 100% | 77% | 0% | High
Pay Grades | Admin can add/edit/delete pay grades with identifying salary ranges. | 100% | 100% | 0% | High
Employment Status | Admin can add/edit/delete employment status. | 100% | 88% | 0% | High
Job Categories | Admin can create/edit/delete job categories. | 100% | 88% | 0% | High
Work Shifts | Admin can assign work shirts for employees. | 100% | 100% | 0% | High
General Information | Admin can edit companies general information. | 100% | 89% | 0% | Medium
Locations | the admin control the Locations feature and perform opreations related to it like (search, add , edit , delete , view ) | 100% | 90% | 0% | High
Structure | the admin control the Structure feature and perform opreations related to the units and sub units like (search, expand, collapes, add , edit , delete , view ) | 100% | 82% | 0% | High
Skills | the admin control the skills feature and perform opreations related to it like ( add , edit , delete , view ) | 100% | 89% | 0% | High
Education | the admin control the Education feature and perform opreations related to it like ( add , edit , delete , view ) | 100% | 90% | 0% | Medium
License | the admin control the License feature and perform opreations related to it like add , edit , delete , view ) | 100% | 90% | 0% | High
Languages | the admin control the Languages feature and perform opreations related to it like (, add , edit , delete , view ) | 100% | 90% | 0% | Medium
Memberships | the admin control the Memberships feature and perform opreations related to it like (add , edit , delete , view ) | 100% | 90% | 0% | High