## Dashboard
Project Name : | Orange HRM
Delivery Date : | 27/6/2025
Release Number : | Release no 01
Designed By : | Nagham,Haya,Abedalrahman,Mohammad
Browsers : | Chrome,Edge,Brave
Android Versions : | -
iOS Versions : | -
Total Number of Test Cases : | 302
Number of Passed Test Cases : | 287
Number of Failed Test Cases : | 15
Number of Blocked Test Cases : | 1
Environment : | Windows 11,10

## Test Cases (Employee)
Test Suite ID | Title | Test Case ID | Test Case Descriprion | Precondition | Test Data | Test Steps | Expected Result | Actual Result | Status | Bug ID
"3.0 | LogIn | 3.0.1 | Login with valid credentials | HR Admin has added the user to the system | Username: Mohammad, Password: Mohammad@123 | 1. Navigate to login page 2. Enter valid username 3. Enter valid password 4. Click on Login button | User should be redirected to the Dashboard | User was redirected to the Dashboard correctly | Pass
|  | 3.0.2 | Login with valid username and invalid password | User is on the login page | Username: Mohammad, Password: 1m1o2oj | 1. Navigate to login page 2. Enter valid username 3. Enter invalid password 4. Click on Login button | System should display error massage | System displayed 'Invalid credentials' | Pass
|  | 3.0.3 | Login with blank fields | User is on the login page | Username: (blank), Password: (blank) | 1. Navigate to login page 2. Click on Login without entering credentials | System should show 'Required' message for both fields | System displayed 'Required' under both fields | Pass
|  | 3.0.4 | Login with capital letters in username | User is on the login page | Username: MOHAMMAD, Password: Mohammad@123 | 1. Navigate to login page 2. Enter capitalized username 3. Enter valid password 4. Click Login | User should be redirected to the Dashboard | User was redirected to the Dashboard correctly | Pass
|  | 3.0.5 | Login with spaces in username | User is on the login page | Username: " Mohammad ", Password: Mohammad@123 | 1. Navigate to login page 2. Enter username with spaces 3. Enter valid password 4. Click Login | System should trim spaces and redirect to Dashboard | User was redirected to the Dashboard correctly | Pass
|  | 3.0.6 | Password field hides input | User is on the login page |  | 1. Navigate to login page 2. Focus on password field 3. Type characters | Input should be masked with asterisks | Password was hidden properly | Pass
|  | 3.0.7 | Login from different browsers | User has valid credentials | Username: Mohammad, Password: Mohammad@123 | 1. Open login page in different browsers (e.g. Chrome, Firefox) 2. Enter credentials 3. Click Login | User should be logged in successfully in all browsers | Login succeeded in all browsers | Pass
|  | 3.0.8 | Login with invalid username | User is on the login page | Username: test76767, Password: Mohammad@123 | 1. Navigate to login page 2. Enter invalid username 3. Enter valid password 4. Click Login | System should display error massage | System displayed 'Invalid credentials' | Pass
|  | 3.0.9 | Login with non-existing account | User is on the login page | Username: test, Password: test123 | 1. Enter non-existing credentials 2. Click Login | System should display error massage | System displayed 'Invalid credentials' | Pass
|  | 3.0.10 | SQL injection in login fields | User is on the login page | Username: ' OR 1=1-- | 1. Enter SQL code in input fields 2. Click Login | System should treat input as string and reject login | System displayed 'Invalid credentials' | Pass
|  | 3.0.11 | Multiple failed login attempts | User repeatedly enters wrong password | Username: Mohammad, Password: wrong (×5) | 1. Enter wrong password multiple times 2. Observe system behavior | System should lock account or display warning | No action was taken | Fail | B1
|  | 3.0.12 | Using browser back after login | User has logged in | Valid credentials | Navigate back using browser after login | System should not return to login page unless logged out | Login page reappeared but was unresponsive | Fail | B2
|  | 3.0.13 | Username & password not shown in URL | User logs in successfully | Valid credentials | 1. Login successfully 2. Observe URL | URL should not contain username/password | Credentials were not shown in URL | Pass
3.1.1 | Personal Details | 3.1.1.1 | Edit editable personal details | ESS-User logged in successfully. | Full Name, License Expiry Date, Other ID | 1. Access 'My Info' > 'Personal Details' 2. Edit editable fields 3. Click 'Save' | Information should be updated successfully with message 'Successfully Updated' | Information updated successfully with message displayed | Pass
|  | 3.1.1.2 | Verify non-editable fields cannot be modified | ESS-User logged in successfully. | Employee ID, Date of Birth, Driver License | 1. Access 'My Info' > 'Personal Details' 2. Try editing non-editable fields | Fields should be disabled and not editable | Fields were non-editable as expected | Pass
|  | 3.1.1.3 | Leave required fields (First and Last Name) empty | ESS-User logged in successfully | First Name: [blank], Last Name: [blank] | 1. Access 'My Info' > 'Personal Details' 2. Clear First and Last Name 3. Click 'Save' | System should display a messages for the required fields | Validation messages displayed for required fields | Pass
|  | 3.1.1.4 | Leave all optional fields empty and save | ESS-User logged in successfully |  | 1. Access 'My Info' > 'Personal Details' 2. Leave optional fields empty 3. Click 'Save' | Information should be saved successfully | Data saved successfully | Pass
|  | 3.1.1.5 | Enter valid License Expiry Date manually | ESS-User logged in successfully | 2020-06-11 | 1. Access 'My Info' > 'Personal Details' 2. Manually enter License Expiry Date 3. Click 'Save' | Date should be accepted and saved successfully | Date accepted and saved | Pass
|  | 3.1.1.6 | Select License Expiry Date using calendar icon | ESS-User logged in successfully | 2020-06-11 | 1. Access 'My Info' > 'Personal Details' 2. Click on calendar icon 3. Select date 4. Click 'Save' | Date should populate and save successfully | Date selected and saved successfully | Pass
|  | 3.1.1.7 | Enter invalid format in License Expiry Date | ESS-User logged in successfully | 00-2-2020 | 1. Access 'My Info' > 'Personal Details' 2. Enter date in wrong format 3. Click 'Save' | System should display error message about incorrect format | Validation error displayed: “Should be a valid date in yyyy-dd-mm format” | Pass
|  | 3.1.1.8 | Select both Male and Female gender | ESS-User logged in successfully |  | 1. Access 'My Info' > 'Personal Details' 2. Try selecting both Male and Female | Only one selection should be allowed | Only one radio button could be selected at a time | Pass
|  | 3.1.1.9 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Access 'My Info' > 'Personal Details' 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.1.10 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.1.11 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.1.12 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.1.13 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.1.14 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.1.15 | Verify 'Records Found' count updates correctly after upload and delete | ESS-User logged in successfully |  | 1. Count current attachments 2. Upload new file 3. Verify count increased 4. Delete a file 5. Verify count decreased | Record count should increase by 1 after upload and decrease by 1 after delete | Count updated correctly | Pass
|  | 3.1.1.16 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.2 | Photograph | 3.1.2.1 | Choose a valid Profile Picture (jpg, png, gif < 1MB) | ESS-User logged in successfully | image.png <1MB | 1. Click on photo area 2. Click '+ icon' 3. Choose a valid picture 4. Click 'Save' | Profile picture should be updated successfully | Profile picture updated successfully | Pass
|  | 3.1.2.2 | Choose invalid profile picture (svg) | ESS-User logged in successfully | image.svg | 1. Click on photo area 2. Click '+ icon' 3. Choose an SVG file 4. Click 'Save' | System should display error message | "File type not allowed" message displayed | Pass
|  | 3.1.2.3 | Click save without choosing any picture | ESS-User logged in successfully | No file selected | 1. Click on photo area 2. Click '+ icon' 3. Click 'Save' without selecting a file | System should display error message | Required message displayed | Pass
|  | 3.1.2.4 | Choose picture > 1MB | ESS-User logged in successfully | image.jpg >1MB | 1. Click on photo area 2. Click '+ icon' 3. Choose a picture larger than 1MB 4. Click 'Save' | System should display error message | "Attachment Size Exceeded" message displayed | Pass
3.1.3 | Contact Details | 3.1.3.1 | Enter valid address details | ESS-User logged in successfully | Street 1: 'sinjel', Street 2: '117', City: 'Ramallah', State: 'Palestine' | 1. Access 'My Info' > 'Contact Details' 2. Enter valid address fields 3. Click 'Save' | Address should be saved successfully | Address saved successfully | Pass
|  | 3.1.3.2 | Enter valid phone numbers within 15 characters | ESS-User logged in successfully | Home: +96261234567 | 1. Access 'My Info' > 'Contact Details' 2. Enter valid numbers 3. Click 'Save' | Phone numbers should be saved successfully | Numbers saved successfully | Pass
|  | 3.1.3.3 | Enter invalid phone number | ESS-User logged in successfully | Mobile: 5 | 1. Access 'My Info' > 'Contact Details' 2. Enter invalid phone format 3. Click 'Save' | System should reject input | Invalid phone accepted | Fail | B3
|  | 3.1.3.4 | Enter valid emails in Work and Other Email fields | ESS-User logged in successfully | admin@example.com | 1. Access 'My Info' > 'Contact Details' 2. Enter valid emails 3. Click 'Save' | Emails should be saved successfully | Emails saved | Pass
|  | 3.1.3.5 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Access 'My Info' > 'Personal Details' 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.3.6 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.3.7 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.3.8 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.3.9 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.3.10 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.3.11 | Verify behavior of "State" field based on selected country | ESS-User logged in successfully | Country = US | 1. Access 'My Info'>'Contact Details' 2. ocate the "Country" dropdown and select United States. | The "State" field should become a dropdown menu with a list of US. States | Field remains manual input for all countries, no dropdown shown. | fail | B4
|  | 3.1.3.12 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Access 'My Info' > 'Personal Details' > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.4 | Emergency Contact | 3.1.4.1 | Enter valid Name, Relationship, and Home Telephone | ESS-User logged in successfully | Name: Ahmad, Relationship: Brother, Home Telephone: 0599999999 | 1. Go to 'My Info' > 'Emergency Contacts' 2. Click 'Add' 3. Enter valid values 4. Click 'Save' | Contact should be added with message "Successfully Saved" | Contact saved successfully | Pass
|  | 3.1.4.2 | Enter invalid characters in phone fields | ESS-User logged in successfully | Phone: "123@aسس" | 1. Go to 'Emergency Contacts' 2. Click 'Add' 3. Enter symbols/letters in phone fields 4. Click 'Save' | System should display error massage | "Allows numbers and only + - / ( )" displayed | Pass
|  | 3.1.4.3 | Leave Name, Relationship, and Home Telephone blank | ESS-User logged in successfully | Blank fields | 1. Go to 'Emergency Contacts' 2. Click 'Add' 3. Leave required fields empty 4. Click 'Save' | System should display required message | Required message displayed | Pass
|  | 3.1.4.4 | Edit existing emergency contact using edit icon | ESS-User with existing contact |  | 1. Go to 'Emergency Contacts' 2. Click edit icon next to contact 3. Modify data 4. Click 'Save' | Info should update and message: "Successfully Updated" should appear | Contact updated successfully | Pass
|  | 3.1.4.5 | Delete an emergency contact using delete icon | ESS-User with existing contact |  | 1. Go to 'Emergency Contacts' 2. Click delete icon next to contact 3. Confirm deletion | Message "Successfully Deleted" should appear | Contact deleted successfully | Pass
|  | 3.1.4.6 | Delete all emergency contacts using "Delete Selected" | ESS-User with multiple contacts |  | 1. Go to 'Emergency Contacts' 2. Select all checkboxes 3. Click "Delete Selected" 4. Confirm | Message "Successfully Deleted" should appear | All contacts deleted | Pass
|  | 3.1.4.7 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Access 'My Info' > ' Emergency Contact' 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.4.8 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Access 'My Info' > ' Emergency Contact' > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.4.9 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Access 'My Info' > ' Emergency Contact' > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.4.10 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.4.11 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.4.12 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.4.13 | Verify 'Records Found' count updates correctly after upload and delete | ESS-User logged in successfully |  | 1. Count current attachments 2. Upload new file 3. Verify count increased 4. Delete a file 5. Verify count decreased | Record count should increase by 1 after upload and decrease by 1 after delete | Count updated correctly | Pass
|  | 3.1.4.14 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Access 'My Info' > ' Emergency Contact' > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.5 | Dependents | 3.1.5.1 | Enter valid Name and Relationship (Child or Other with Specify) | ESS-User logged in successfully | Name :Ahmad, Specify"brother" | 1. Go to 'My Info' > 'Dependents' 2. Click 'Add' 3. Enter valid Name 4. Select Relationship 5. If 'Other', enter Specify 6. Click 'Save' | Dependent should be saved with message "Successfully Saved" | Saved as expected | Pass
|  | 3.1.5.2 | Leave required fields empty (Name, Relationship, Specify if Other) | ESS-User logged in successfully | All required fields blank | 1. Go to 'Dependents' 2. Click 'Add' 3. Leave Name, Relationship, or Specify blank 4. Click 'Save' | System should display required message | Required message displayed | Pass
|  | 3.1.5.3 | Enter valid Date of Birth manually | ESS-User logged in successfully | Date: 2010-05-10 | 1. Go to 'Dependents' 2. Enter DOB manually 3. Click 'Save' | Date should be saved successfully | Date saved correctly | Pass
|  | 3.1.5.4 | Select Date of Birth using calendar icon | ESS-User logged in successfully | Date: 2010-05-10 | 1. Go to 'Dependents' 2. Open calendar 3. Select a date 4. Click 'Save' | Date should be saved successfully | Date saved correctly | Pass
|  | 3.1.5.5 | Enter invalid format in Date of Birth | ESS-User logged in successfully | Date: 00/00/2010 | 1. Go to 'Dependents' 2. Enter date in invalid format 3. Click 'Save' | system shold display error massage | system displayed "Should be a valid date in yyyy-dd-mm format" | Pass
|  | 3.1.5.6 | Edit a dependent using edit icon | ESS-User with existing dependent |  | 1. Go to 'Dependents' 2. Click edit icon next to a dependent 3. Modify field 4. Save | System should show "Successfully Updated" | Dependent updated successfully | Pass
|  | 3.1.5.7 | Delete a dependent using delete icon | ESS-User with existing dependent |  | 1. Go to 'Dependents' 2. Click delete icon 3. Confirm deletion | System should show "Successfully Deleted" | Deleted successfully | Pass
|  | 3.1.5.8 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Access 'My Info' > 'Dependents' 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.5.9 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Access 'My Info' > 'Dependents' > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.5.10 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Access 'My Info' > 'Dependents' > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.5.11 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.5.12 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.5.13 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.5.14 | Verify 'Records Found' count updates correctly after upload and delete | ESS-User logged in successfully |  | 1. Count current attachments 2. Upload new file 3. Verify count increased 4. Delete a file 5. Verify count decreased | Record count should increase by 1 after upload and decrease by 1 after delete | Count updated correctly | Pass
|  | 3.1.5.15 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Access 'My Info' > 'Dependents' > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.6 | Immigration | 3.1.6.1 | Enter valid Passport or Visa data | ESS-User logged in successfully | Document: Passport or Visa Number: '123456' Valid dates format | 1. Go to 'Immigration' 2. Click 'Add' 3. Select Passport or Visa 4. Enter valid Number and valid dates 5. Click 'Save' | Immigration record should be saved with message 'Successfully Saved' | Record saved correctly | Pass
|  | 3.1.6.2 | Enter letters in 'Number' field | ESS-User logged in successfully | Number: 'ABCD1234' | 1. Go to 'Immigration' 2. Click 'Add' 3. Enter letters in Number field 4. Click 'Save' | System should reject it and display error message | Letters accepted in Number field | Fail | B5
|  | 3.1.6.3 | Click 'Save' without entering required Number field | ESS-User logged in successfully | Number: [empty] | 1. Go to 'Immigration' 2. Click 'Add' 3. Leave Number empty 4. Click 'Save' | System should display required message | Required message displayed | Pass
|  | 3.1.6.4 | Edit Immigration record using edit icon | ESS-User with existing immigration record |  | 1. Go to 'Immigration' 2. Click edit icon next to record 3. Modify data 4. Click 'Save' | Record should be updated with message 'Successfully Updated' | Record updated correctly | Pass
|  | 3.1.6.5 | Delete Immigration record using delete icon | ESS-User with existing immigration record |  | 1. Go to 'Immigration' 2. Click delete icon next to record 3. Confirm deletion | Record should be deleted with message 'Successfully Deleted' | Record deleted correctly | Pass
|  | 3.1.6.6 | Enter invalid format in any date field (e.g. 00-02-2020) | ESS-User logged in successfully | Issued Date: '00-02-2020' | 1. Go to 'Immigration' 2. Enter invalid date 3. Click 'Save' | System should display error massage | "Should be a valid date in yyyy-dd-mm format" displayed | Pass
|  | 3.1.6.7 | Select Passport and Visa together | ESS-User logged in successfully |  | 1. Try selecting both radio buttons for Passport and Visa | Only one option should be selectable at a time | Only one selection allowed | Pass
|  | 3.1.6.8 | Delete multiple attachments at once | ESS-User logged in successfully with multiple attachments uploaded |  | 1. Go to My Info > Immigration 2. Scroll to 'Attachments' section 3. Select multiple files using checkboxes 4. Click 'Delete selected' icon | All selected attachments should be deleted | Files were successfully deleted | pass
|  | 3.1.6.9 | Upload supported file as attachment | ESS-User logged in successfully | File: sample.pdf | 1. Go to My Info > Immigration > 'Add Attachment'2. Upload supported file3. Click 'Save' | File should be uploaded and listed in the table | PDF uploaded successfully | Pass
|  | 3.1.6.10 | Upload unsupported file type (SVG) | ESS-User logged in successfully | File: logo.svg | 1. Go to My Info > Immigration > 'Add Attachment'2. Upload unsupported file3. Click 'Save' | System should reject the file and show error: "File type not allowed" | Error message displayed as expected | Pass
|  | 3.1.6.11 | Edit uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click edit icon3. Update comment4. Save changes | Comment should be updated successfully | Comment updated | Pass
|  | 3.1.6.12 | Delete uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click delete icon on a file3. Confirm deletion | File should be removed from list and table updates | File deleted successfully | Pass
|  | 3.1.6.13 | Download uploaded attachment | ESS-User logged in successfully with existing attachment |  | 1. Access attachment table2. Click download icon on a file | File should be downloaded successfully | File downloaded | Pass
|  | 3.1.6.14 | Verify "Issued Date" does not accept future dates | ESS-User logged in successfully | Issued Date = future date (11-11-2025) | 1.Go to My Info > Immigration2. Click on Add3. Enter a future date in the Issued Date field4. Click Save | System should reject future dates and show an error message. | System accepts the future date without any validation. | Fail | B6
|  | 3.1.6.15 | Upload attachment with size > 1MB | ESS-User logged in successfully | Upload file > 1MB | 1. Go to My Info > Immigration > 'Add Attachment' 2. Upload a file larger than 1MB 3. Click 'Save' | System should reject file and display error message | Error message 'Attachment Size Exceeded' displayed | Pass
3.1.7 | Job Details | 3.1.7.1 | verify that the Job button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Log in then Navigate to “My Info” | The Job section should appear to the user | As expected | Pass
|  | 3.1.7.2 | Verify visibility of job information | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “Job” | All job details are displayed correctly | As expected | Pass
|  | 3.1.7.3 | Verify that job fields are not editable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Attempt to click or edit any job detail field | Fields are read-only; no editable fields present | As expected | Pass
|  | 3.1.7.4 | Ensure absence of Edit/Save/Delete buttons | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Check for action buttons in the Job section | No Edit, Save, or Delete buttons exist | As expected | Pass
|  | 3.1.7.5 | Ensure "Include Employment Contract Details" button is clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “Job”→ enable Include Employment Contract Details button | The information of the contract should appear when the user enable the button | As expected | Pass
3.1.8 | Salary | 3.1.8.1 | verify that the slary button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | log in then Navigate to “My Info” | The salary section should appear to the user | As expected | Pass
|  | 3.1.8.2 | Verify visibility of Salary information | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “salary” | All salary details are displayed correctly | As expected | Pass
|  | 3.1.8.3 | Verify salary details section is not editable for EES | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “salary” | information field is completely hidden from the ESS-User | As expected | Pass
|  | 3.1.8.4 | Test direct URL access to salary page | A Browser | RRL : https://opensource-demo.orangehrmlive.com/web/index.php/pim/viewSalaryList/empNumber/7 | Enter direct salary URL in browser | User receives access denied or is redirected | As expected | Pass
3.1.9 | Report To | 3.1.9.1 | verify that the "Report to"button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | log in then Navigate to “My Info” → Look for Report to section | The Report to section should appear to the user | As expected | Pass
|  | 3.1.9.2 | Verify supervisors are listed | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “Report To” section | Supervisor list is displayed | As expected | Pass
|  | 3.1.9.3 | View subordinates if user is also a supervisor | ESS-User is also supervisor | username=nnnnn Password=nnnnn12345 | Navigate to “Report To” → Look for subordinate section | Subordinate list is displayed | As expected | Pass
|  | 3.1.9.4 | Ensure fields are read-only | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Try editing fields like Assigned Supervisor or Subordinate | Fields are disabled BUT not editable | As expected | Pass
3.1.10 | Qualifications | 3.1.10.1 | verify that the "Qualifications"button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | log in then Navigate to “My Info” → Look for Qualifications section | The Report to section should appear to the user | As expected | Pass
|  | 3.1.10.2 | Verify visibility of Qualifications information | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “Qualifications ” | All Qualifications details are displayed correctly | As expected | Pass
|  | 3.1.10.3 | Add valid work experience | ESS-User is logged in | Company: ABC Ltd, Job Title: QA Engineer, From: 01/01/2020, To: 01/01/2022 | Navigate to My Info > Qualifications > Work Experience > Click Add > Fill all fields > Click Save | The work experience should be added sucessfully | As expected | Pass
|  | 3.1.10.4 | Add multiple work experiences | User has one existing entry | Company: XYZ Inc, Job Title: Tester | Navigate to My Info > Qualifications > Work Experience > Click Add > Fill all fields > Click Save | Both entries are listed under Work Experience | As expected | Pass
|  | 3.1.10.5 | Add experience with missing required field | ESS-User is logged in | Leave 'Job Title' empty | Navigate to My Info > Qualifications > Work Experience >Click Add > Leave Job Title blank > Click Save | Error message: 'Job Title is required' | As expected | Pass
|  | 3.1.10.6 | Add experience with future date | ESS-User is logged in | From Date: 01/01/2026 | Navigate to My Info > Qualifications > Work Experience >Click Add > Enter future date > Click Save | Validation error: 'Date cannot be in the future' | Date Addedd successfully | Fail | B7
|  | 3.1.10.7 | Delete single work experience entry | At least one entry exists |  | Select one entry > Click Delete > Confirm | Selected entry is deleted and removed from list | As expected | Pass
|  | 3.1.10.8 | Delete multiple work experience entries | Multiple entries exist |  | Select multiple checkboxes > Click Delete > Confirm | All selected entries are removed | As expected | Pass
|  | 3.1.10.9 | Delete multiple work experience entries | Multiple entries exist |  | Select multiple checkboxes > Click Delete > Confirm | All selected entries are removed | As expected | Pass
|  | 3.1.10.10 | Verify comment section doesnt accept morre than 200 characters | ESS-User is logged in | comment : my current job is qa let it be more than 200 char | Navigate to My Info > Qualifications > Work Experience >Click Add > add comment | An error msg that tell the user about the chars limit | As expected | Pass
|  | 3.1.10.11 | Edit work experience entry | work experience entry |  | Navigate to My Info > Qualifications > Work Experience > Click edit entery | The work experience should be edited successfully | As expected | Pass
|  | 3.1.10.12 | Add valid education | ESS-User is logged in | Level : BSc, Institute:Birzeit , Year:2020 | Go to Education > Add > Fill all fields > Save | Entry is added to the list | As expected | Pass
|  | 3.1.10.13 | Save with missing requiered field | ESS-User is logged in |  | Go to Education > Add > Leave school blank > Save | Error: 'This feild is required' | As expected | Pass
|  | 3.1.10.14 | Delete education entry | At least one entry |  | Select entry > Click Delete | Entry is removed from the list | Doesnt Remove with msg that say the entery is not exist while its exsist | Fail | B8
|  | 3.1.10.15 | Add a year using words instead of numbers | ESS-User is logged in | year : twenty twenty | Go to Education > Add > Year | Error : enter numbers | As expected | pass
|  | 3.1.10.16 | Add GPA/Score using words instead of numbers | ESS-User is logged in | year : twenty twenty | Go to Education > Add > Year | Error : enter numbers | Addedd successfully | Fail | B9
|  | 3.1.10.17 | Add a new skill | ESS-User is logged in | Skill: Automation Testing | Go to Skills > Add > Fill skill > Save | Skill is added to the list | As expected | pass
|  | 3.1.10.18 | Add duplicate skill | Skill already exists | Skill: Automation Testing | Try adding same skill again | Duplicate entry error or allowed | As expected | pass
|  | 3.1.10.19 | Delete skill | At least one entry |  | Select skill > Click Delete | Skill is removed | As expected | pass
|  | 3.1.10.20 | Edit skill entry | skill entry |  | Navigate to My Info > Qualifications > Work Experience > Click edit entery | The skill should be edited successfully | As expected | pass
|  | 3.1.10.21 | Add new language with level | ESS-User is logged in | Language: English, Fluency: reading ,Competency:poor | Go to Languages > Add > Fill fields > Save | Language is listed | As expected | pass
|  | 3.1.10.22 | Add language without level | ESS-User is logged in | Language: English, Fluency: reading ,Competency:poor | Go to Languages > Add > Leave level empty > Save | Error: 'Level is required' | As expected | pass
|  | 3.1.10.23 | Delete language | At least one entry |  | Select language > Click Delete | Language entry is removed | As expected | pass
|  | 3.1.10.24 | Add a license entry | ESS-User is logged in | License: ISTQB, Date: 01/01/2021 | Go to Licenses > Add > Fill fields > Save | License is added to list | As expected | pass
|  | 3.1.10.25 | Add license with missing name | ESS-User is logged in | LicenseType : (empty) | Attempt to save license form | Error: 'License Name required' | As expected | pass
|  | 3.1.10.26 | Delete license | At least one entry |  | Select license > Click Delete | License is removed | As expected | pass
|  | 3.1.10.27 | Upload valid attachment | ESS-User is logged in | File: certificate.pdf (400KB) | Go to Attachments > Add > Upload file > Click Upload | File is listed under attachments | As expected | pass
|  | 3.1.10.28 | Upload file >1MB | ESS-User is logged in | File: largefile.pdf (1.5MB) | upload file >1MB | Error shown: 'File size exceeds limit' | As expected | pass
|  | 3.1.10.29 | Upload unsupported file type | ESS-User is logged in | File: script.exe | upload unsupported file | Error shown: 'Unsupported file type' | As expected | pass
|  | 3.1.10.30 | Delete uploaded attachment | Attachment exists | N/A | Select attachment > Click Delete | Attachment is removed | As expected | pass
3.1.11 | Membership | 3.1.11.1 | verify that the "Membership"button is appear for the user and it's clickable | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | log in then Navigate to “My Info” → Look for Membership section | The Membership section should appear to the user | As expected | pass
|  | 3.1.11.2 | Verify visibility of Membership information | ESS-User is logged in | username=nnnnn Password=nnnnn12345 | Navigate to “My Info” → Click on “Membership ” | All Membership details are displayed correctly | As expected | pass
|  | 3.1.11.3 | Add a new membership entry | User logged in, on Membership page | Membership: ACCA Sub: 100 Currency: USD Start Date: 01/01/2024 | 1. Click “Add” 2. Enter all required data 3. Click “Save” | Membership is listed under membership table | As expected | pass
|  | 3.1.11.4 | Add multiple membership entries | User on Membership page | Membership:CIM,CIMA | Repeat steps above for each entry | All entries appear in the membership list | As expected | pass
|  | 3.1.11.5 | Submit form with missing required field | User on Add Membership form | Membership field left blank | 1. Click “Add” 2. Leave Membership field empty 3. Click “Save” | Validation error is displayed, This field is required | As expected | pass
|  | 3.1.11.6 | Upload a valid attachment | User on Add Membership form | File: cert.pdf | 1. Click “Add” under Attachment 2. Select valid file 3. Click “Upload” | File is uploaded and displayed under the entry | As expected | pass
|  | 3.1.11.7 | Upload an invalid file type | User on Add Membership form | File: file.exe | 1. Click “Add” under Attachment 2. Select invalid file 3. Click “Upload” | Upload fails, error message shown : file type not allowed | As expected | pass
|  | 3.1.11.8 | Delete a single membership entry | At least 1 membership entry exists | N/A | 1. Tick checkbox for one entry 2. Click “Delete” | Entry is deleted from the list | As expected | pass
|  | 3.1.11.9 | Delete multiple membership entries | Multiple entries exist | N/A | 1. Tick multiple checkboxes 2. Click “Delete” | Selected entries are deleted from the list | As expected | pass
|  | 3.1.11.10 | Verify file opens after upload | Attachment is uploaded | File: cert.pdf | 1. Click uploaded file 2. Verify it opens | File opens successfully | As expected | pass
|  | 3.1.11.11 | Cancel add membership | On Add Membership form | Fill some fields only | 1. Click “Add” 2. Enter partial info 3. Click “Cancel” | Form closes, no new membership is added | As expected | pass
|  | 3.1.11.12 | Validate numeric field format | On Add Membership form | Subscription amount: ABC | 1. Click “Add” 2. Enter letters in Subscription field 3. Click “Save” | Validation message: only numbers are allowed | As expected | pass
|  | 3.1.11.13 | Edit Membership entry | Membership entry |  | Navigate to My Info > Membership> Work Experience > Click edit entery | The Membership should be edited successfully | As expected | pass

## Test Cases (Admin)
Test Suite ID | Title | Test Case ID | Test Case Descriprion | Precondition | Test Data | Test Steps | Expected Result | Actual Result | Status | Bug ID | Notes
R3.2.1 | ADD USER | TC1 | Create user by admin and customize it as admin with valid data | Login as admin + Admin Page + Add User | User Role: Admin Employee Name Status: Enable Unique Username Password: Peter123 Password Confimation: Peter123 | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter valid inputs 5. Save | Add User as admin, New Admin can login | Cant create user, Because Employee Name is restricted by Lists (Type for Hints) | Fail | B1
|  | TC2 | Create user by admin and customize it as admin with valid data | Login as admin + Admin Page + Add User | User Role: Admin Choose Employee Name from hints Status: Enable Unique Username Password: Peter123 Password Confimation: Peter123 | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter valid inputs 5. Save | Add User as admin, New Admin can login | Add User as admin, New Admin can login | Pass
|  | TC3 | Create user by admin and customize it as ESS with valid data | Login as admin + Admin Page + Add User | User Role: ESS Choose Employee Name from hints Status: Enable Unique Username Password: Jacki123 Password Confimation: Jacki123 | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter valid inputs 5. Save | Add User as ESS, New ESS can login | Add User as ESS, New ESS can login | Pass
|  | TC4 | Create user by admin and customize it as admin/ESS with making it disabled | Login as admin + Admin Page + Add User | User Role: Admin/ESS Choose Employee Name from hints Status: Disable Unique Username Password: Hello1gg Password Confimation: Hello1gg | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter invalid inputs by making status disable 5. Save | Add User as admin/ESS, New user can't login | Add User as admin/ESS, New user can't login | Pass
|  | TC5 | Password Mismatch | Login as admin + Admin Page + Add User | User Role: Admin/Employee Choose Employee Name from hints Status: Enable Unique Username Password: Gaza1gg Password Confimation: aaaa1gg | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter invalid inputs 5. Save | Warning Message: "Passwords do not match" + No Save | Warning Message: "Passwords do not match" + No Save | Pass
|  | TC6 | Password Complexity | Login as admin + Admin Page + Add User | User Role: Admin/Employee Choose Employee Name from hints Status: Enable Unique Username Password: 123 Password Confimation: 123 | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter invalid inputs 5. Save | Warning Message: "Should have at least 7 characters" + No Save | Warning Message: "Should have at least 7 characters" + No Save | Pass
|  | TC7 | Duplicate Username | Login as admin + Admin Page + Add User | User Role: Admin/Employee Choose Employee Name from hints Status: Enable Duplicate Username Password: 123Jack Password Confimation: 123Jack | 1. Login as admin 2. Open admin page 3. Add Button 4. Enter invalid inputs 5. Save | Warning Message: "Already Exists" + No Save | Warning Message: "Already Exists" + No Save | Pass
|  | TC8 | Missing Required Fields | Login as admin + Admin Page + Add User | Leave one field blank at a time | 1. Login as admin 2. Open admin page 3. Add Button 4. Empty input 5. Save | Warning Message: "Required Field" + No Save | Warning Message: "Required Field" + No Save | Pass |  | Test each field separately.
|  | TC9 | Long Username | Login as admin + Admin Page + Add User | User Role: Choose Employee Name from hints Status: Enable Username: JackJackJackJackJack Password: 123Jack Password Confimation: 123Jack | 1. Login as admin 2. Open admin page 3. Add Button 4. edge case 5. Save | Warning Message: "Should not exceed 40 characters" + No Save | Warning Message: "Should not exceed 40 characters" + No Save | Pass
|  | TC10 | Long Password | Login as admin + Admin Page + Add User | User Role: Admin/ESS Choose Employee Name from hints Status: Enable Username: user123 Password: 123Jack123Jack123Jack123Jack Password Confimation: 123Jack123Jack123Jack123Jack | 1. Login as admin 2. Open admin page 3. Add Button 4. edge case 5. Save | Warning Message: "Should not exceed 64 characters" + No Save | Warning Message: "Should not exceed 64 characters" + No Save | Pass
| DELETE USER | TC11 | Delete single Admin user | Login as admin + Admin Page + Delete User | Delete Admin User | 1. Login as admin 2. Open admin page 3. Delete Admin User | Admin user removed from list | Admin user removed from list | Pass
|  | TC12 | Delete single ESS user | Login as admin + Admin Page + Delete User | Delete ESS User | 1. Login as admin 2. Open admin page 3. Delete ESS User | ESS user removed from list | ESS user removed from list | Pass
|  | TC13 | Delete Admin & ESS users | Login as admin + Admin Page + Delete User | Delete Admin & ESS users | 1. Login as admin 2. Open admin page 3. Delete Admin & ESS users | Admin & ESS users removed from list | Admin & ESS users removed from list | Pass
|  | TC14 | Delete All | Login as admin + Admin Page + Delete User | Delete All | 1. Login as admin 2. Open admin page 3. Delete All | All removed from list except Current Admin | All removed from list except Current Admin | Pass
|  | TC15 | Delete with no selection | Login as admin + Admin Page + Delete User | Delete with no selection | 1. Login as admin 2. Open admin page 3. Delete with no selection | No Delete | No Delete | Pass
|  | TC16 | Delete user then Verify login blocked | Login as admin + Admin Page + Delete User | Username/Password of deleted user | Attempt login with deleted user credentials | Error: "Invalid credentials" or "Account not found" | Error: "Invalid credentials" or "Account not found" | Pass
|  | TC17 | Delete current admin (self) | Login as admin + Admin Page + Delete User | Delete current admin | 1. Login as admin 2. Open admin page 3. Delete current user | warning message: "Cant be deleted" | warning message: "Cant be deleted" | Pass
| EDIT USER | TC18 | Edit username (valid) | Login as admin + Admin Page + Edit User | New username: John_updated | 1. Login as admin 2. Open admin page 3. Edit User 4. username | username updated | username updated | Pass
|  | TC19 | Change role (Admin → ESS) | Login as admin + Admin Page + Edit User | Role: ESS | 1. Login as admin 2. Open admin page 3. Edit User 4. user role | role updated | role updated | Pass
|  | TC20 | Edit Employee Name | Login as admin + Admin Page + Edit User | Employee Name: John | 1. Login as admin 2. Open admin page 3. Edit User 4. employee name | Employee name changed | No records found (dropdown list) | Fail | B2 | Same Bug as TC1
|  | TC21 | Change the status of the employee | Login as admin + Admin Page + Edit User | status disabled | 1. Login as admin 2. Open admin page 3. Edit User 4. status | changed | changed | Pass
|  | TC22 | check the login of the disable employee | Login as admin + Admin Page + Edit User | status disabled | 1. Login as admin 2. Open admin page 3. Edit User 4. status | cant login Warning Message: "Account disabled " | cant login Warning Message: "Account disabled " | Pass
|  | TC23 | chage password | Login as admin + Admin Page + Edit User | New Pass: Test123 Confirm Pass: Test123 | 1. Login as admin 2. Open admin page 3. Edit User 4. password | password changed | password changed | Pass
|  | TC24 | Password mismatch | Login as admin + Admin Page + Edit User | New Pass: Test321 Confirm Pass: Murad123 | 1. Login as admin 2. Open admin page 3. Edit User 4. password | "Passwords do not match." No save. | "Passwords do not match." No save. | Pass
|  | TC25 | Duplicate username | Login as admin + Admin Page + Edit User | Username: Test _ Updated | 1. Login as admin 2. Open admin page 3. Edit User 4. username | username exist | username exist | Pass
|  | TC26 | Clear required field | Login as admin + Admin Page + Edit User | Leave one field blank at a time | 1. Login as admin 2. Open admin page 3. Edit User 4. left one blank empty | Warning Message: "Required Field" + No Save | Warning Message: "Required Field" + No Save | Pass
R3.2.2.1 | Add Job | TC27 | Add valid job title | Login as admin + (Job) Job Titles + Add | Job Title: Software Engineer Description: Develops applications | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Added Job | Added Job | Pass
|  | TC28 | Add job title without description/specification/note | Login as admin + (Job) Job Titles + Add | Job Title: QA Analyst | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Added Job | Added Job | Pass
|  | TC29 | Duplicate Job Title | Login as admin + (Job) Job Titles + Add | Job Title: Software Engineer | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Job Title exist | Job Title exist | Pass
|  | TC30 | Empty Field/s | Login as admin + (Job) Job Titles + Add | Blank field/s | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Field is required + No Save | Field is required + No Save | Pass
|  | TC31 | Add long job title more than 100 char | Login as admin + (Job) Job Titles + Add | More than 100 char in job title | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Should not exceed 100 characters | Should not exceed 100 characters | Pass
|  | TC32 | Special chars in job title | Login as admin + (Job) Job Titles + Add | A@@a | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | Cant accept special chars | Added Job | Fail | B2
|  | TC33 | Upload File | Login as admin + (Job) Job Titles + Add | Upload File | 1. Login as admin 2. Open admin page 3. Job Title 4. Add button | File Uploaded | File not uploaded | Fail
| Edit Job | TC34 | Edit job title | Login as admin + (Job) Job Titles + Edit | New Job Title: UX Designer New Description: User experience focus | 1. Login as admin 2. Open admin page 3. Job Title 4. Edit icon | Edited | Edited | Pass
|  | TC35 | Reply same test cases for Add | Login as admin + (Job) Job Titles + Edit | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. Edit icon | Edited | Edited | Fail | B2 | Same Bugs
| Delete Job | TC36 | Delete Job | Login as admin + (Job) Job Titles + Delete | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. delete icon | Deleted | Deleted | Pass
|  | TC37 | Delete 2 Jobs | Login as admin + (Job) Job Titles + Delete | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. delete icon | Deleted | Deleted | Pass
|  | TC38 | Delete All | Login as admin + (Job) Job Titles + Delete | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. delete icon | Deleted | Deleted | Pass
|  | TC39 | Delete no selection | Login as admin + (Job) Job Titles + Delete | N/A | 1. Login as admin 2. Open admin page 3. Job Title 4. delete icon | No Delete | No Delete | Pass
R3.2.2.2 | Add Pay Grade | TC40 | Add valid pay grade | Login as admin + (Job) Pay Grades + Add | P1 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Pay Grade added, Show currency form | Pay Grade added, Show currency form | Pass
|  | TC41 | Add currency to pay grade (valid) | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: 3000 Max Salary: 6000 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Currency added | Currency added | Pass
|  | TC42 | Max smaller than Min salary (invalid) | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: 6000 Max Salary: 3000 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Warnin Message | Warnin Message | Pass
|  | TC43 | Add multiple currencies | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: 3000 Max Salary: 6000 --- Currency: SAR Min Salary: 2000 Max Salary: 5000 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Added | Added | Pass
|  | TC44 | Negative salary values | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: -12 Max Salary: -1 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Warnin Message | Warnin Message | Pass
|  | TC45 | Duplicate currency in pay grade | Login as admin + (Job) Pay Grades + Add | P1 Currency: USD Min Salary: 3000 Max Salary: 6000 --- Currency: USD Min Salary: 3000 Max Salary: 6000 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Enter Pay Greade Name 5. save | Not acceptable | Not acceptable | Pass
| Delete Pay Grade | TC46 | Delete single currency | Login as admin + (Job) Pay Grades + Delete | N/A | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Delete | Deleted | Deleted | Pass
|  | TC47 | delete all currencies | Login as admin + (Job) Pay Grades + Delete | N/A | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Delete | Deleted | Deleted | Pass
|  | TC48 | Delete entire pay grade | Login as admin + (Job) Pay Grades + Delete | N/A | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Delete | Deleted | Deleted | Pass
|  | TC49 | Delete all grades | Login as admin + (Job) Pay Grades + Delete | N/A | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Delete | Deleted | Deleted | Pass
| Edit Pay Grade | TC50 | Edit pay grade name P1 | Login as admin + (Job) Pay Grades + Edit | P100 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Edit Pay grade | updated | updated | Pass
|  | TC51 | Edit currency details | Login as admin + (Job) Pay Grades + Edit | New Min: 3500 New Max: 6500 | 1. Login as admin 2. Open admin page 3. Pay Grades 4. Edit Pay grade | updated | updated | Pass
R3.2.2.3 | Add Employment Status | TC52 | Add valid employment status | Login as admin + (Job) Employment Status + Add | Full-Time | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Added | Added | Pass
|  | TC53 | Add duplicate employment status | Login as admin + (Job) Employment Status + Add | Full-Time | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Warning Message Already exists | Warning Message Already exists | Pass
|  | TC54 | Add long status name more than 100 chars | Login as admin + (Job) Employment Status + Add | More than 100 char in status | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Warning Message Should not exceed 50 characters | Warning Message Should not exceed 50 characters | Pass
|  | TC55 | Special chars in status name | Login as admin + (Job) Employment Status + Add | Full@Time | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Warning Message Cant include special chars except "-" | Added | Fail | B3
|  | TC56 | Add empty status | Login as admin + (Job) Employment Status + Add | Empty | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add | Required | Required | Pass
| Delete Employment Status | TC57 | Delete single status | Login as admin + (Job) Employment Status + Delete | N/A | 1. Login as admin 2. Open admin page 3. Employement Status 4. Delete | Deleted | Deleted | Pass
|  | TC58 | delete all statuses | Login as admin + (Job) Employment Status + Delete | N/A | 1. Login as admin 2. Open admin page 3. Employement Status 4. Delete | Deleted | Deleted | Pass
|  | TC59 | delete with no selection | Login as admin + (Job) Employment Status + Delete | N/A | 1. Login as admin 2. Open admin page 3. Employement Status 4. Delete | Not Deleted | Not Deleted | Pass
| Edit Employment Status | TC60 | Edit employment status | Login as admin + (Job) Employment Status + Edit | Edit from Fulltime to Full Time | 1. Login as admin 2. Open admin page 3. Employement Status 4. Edit | Edited | Edited | Pass
R3.2.2.4 | Add Job Categories | TC61 | Add valid job category | Login as admin + (Job) job category + Add | BackEnd | 1. Login as admin 2. Open admin page 3. job category 4. Add | Added | Added | Pass
|  | TC62 | Add duplicate job category | Login as admin + (Job) job category + Add | BackEnd | 1. Login as admin 2. Open admin page 3. job category 4. Add | Warning Message Already exists | Warning Message Already exists | Pass
|  | TC63 | Add long job name more than 100 chars | Login as admin + (Job) job category + Add | More than 100 char in status | 1. Login as admin 2. Open admin page 3. job category 4. Add | Warning Message Should not exceed 50 characters | Warning Message Should not exceed 50 characters | Pass
|  | TC64 | Special chars in job name | Login as admin + (Job) job category + Add | Data$$Analyst | 1. Login as admin 2. Open admin page 3. job category 4. Add | Warning Message Cant include special chars except "-" | Added | Fail | B3 | Same bug as TC55
|  | TC65 | Add empty status | Login as admin + (Job) job category + Add | Empty | 1. Login as admin 2. Open admin page 3. job category 4. Add | Required | Required | Pass
| Delete Job Categories | TC66 | Delete single job | Login as admin + (Job) job category + Delete | N/A | 1. Login as admin 2. Open admin page 3. job category 4. Delete | Deleted | Deleted | Pass
|  | TC67 | delete all job | Login as admin + (Job) job category + Delete | N/A | 1. Login as admin 2. Open admin page 3. job category 4. Delete | Deleted | Deleted | Pass
|  | TC68 | delete with no selection | Login as admin + (Job) job category + Delete | N/A | 1. Login as admin 2. Open admin page 3. job category 4. Delete | Not Deleted | Not Deleted | Pass
| Edit Job Categories | TC69 | Edit job title | Login as admin + (Job) job category + Edit | Edit from Backend to Back End | 1. Login as admin 2. Open admin page 3. job category 4. Edit | Edited | Edited | Pass
R3.2.2.5 | Add Work Shift | TC70 |  | Login as admin + (Job) Work Shift + Add | Shift Name: Morning Working Hours: 08:00 AM - 05:00 PM | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Added | Added | Pass
|  | TC71 | Add shift with missing required fields | Login as admin + (Job) Work Shift + Add | Shift Name: Evening Working Hours: Empty | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Required Field | Required Field | Pass
|  | TC72 | Assign employee to shift | Login as admin + (Job) Work Shift + Add | Shift Name: Evening Working Hours: 06:00 PM - 11:00 PM | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Added | Added | Pass
|  | TC73 | Add overlapping shift times | Login as admin + (Job) Work Shift + Add | Shift Name: Evening Working Hours: 11:00 PM - 07:00 PM | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Warning Message | Warning Message | Pass
|  | TC74 | Assign employee to multiple shifts | Login as admin + (Job) Work Shift + Add | Ranga Akunuri | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | employee name will not appear in other messages | employee name will not appear in other messages | Pass
| Edit Work Shift | TC75 | Edit shift details | Login as admin + (Job) Work Shift + Edit | Evenin to Evening Shift | 1. Login as admin 2. Open admin page 3. Work Category 4. Edit | Edited | Edited | Pass
|  | TC76 | Remove employee from shift | Login as admin + (Job) Work Shift + Add | N/A | 1. Login as admin 2. Open admin page 3. Work Category 4. Add | Removed | Removed | Pass
| Delete Work Shift | TC77 | Delete single shift | Login as admin + (Job) Work Shift + Delete | N/A | 1. Login as admin 2. Open admin page 3. Work Category 4. Delete | Deleted | Deleted | Pass
|  | TC78 | Delete All | Login as admin + (Job) Work Shift + Delete | N/A | 1. Login as admin 2. Open admin page 3. Work Category 4. Delete | Deleted | Deleted | Pass
|  | TC79 | delete with no selection | Login as admin + (Job) Work Shift + Delete | N/A | 1. Login as admin 2. Open admin page 3. Work Category 4. Delete | Cant Delete | Cant Delete | Pass
R3.2.3.1 | Edit General Information | TC80 | Edit general information with valid data | Login as admin + (Organization) General Information + Edit | Valid Inputs in all fields | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Edited | Edited | Pass
|  | TC81 | Edit with invalid email format | Login as admin + (Organization) General Information + Edit | Info@orangehrm.a | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warning Message | Accept the email | Fail
|  | TC82 | Edit with invalid phone format | Login as admin + (Organization) General Information + Edit | 132iugiug | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warning Message | Warning Message | Pass
|  | TC83 | Partial update of information | Login as admin + (Organization) General Information + Edit | invalid data | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Edited | Edited | Pass
|  | TC84 | Cancel editing without saving | Login as admin + (Organization) General Information + Edit | N/A | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Should not Eexcept, specially if there is a warning message | Accept Data | Pass
|  | TC85 | Verify field length limits | Login as admin + (Organization) General Information + Edit | Enter More than 100 char | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warnin message | Warnin message | Pass
|  | TC86 | Verify required fields | Login as admin + (Organization) General Information + Edit | Name is just required | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warnin message | Warnin message | Pass
|  | TC87 | Verify special characters in fields | Login as admin + (Organization) General Information + Edit | @@@ | 1. Login as admin 2. Open admin page 3. General information 4. Edit | Warning Message | Warning Message | Pass
|  | TC88 | Verify country dropdown list | Login as admin + (Organization) General Information + Edit | N/A | 1. Login as admin 2. Open admin page 3. General information 4. Edit | choosed from the list | choosed from the list | Pass
R3.2.3.2 | location feature | T1.1 | Admin successfully adds a new location | 1. Admin is logged in. 2. "Locations" page is accessible. | Name (Required) City Zip/Postal code phone address State/Province Country (Required) Fax Notes | 1. Navigate to Admin > Organization > Locations. 2. Click + Add. 3. Enter valid data. 4. Click Save. | New location is saved and appears in the list. | New location is saved and appears in the list. | Passed
|  | T1.2 | Admin edits an existing location | 1. At least one location exists. | Original City Updated City | 1. Select "Gaza Office". 2. Click Edit. 3. Update City field "Jersalum" . 4. Click Save. | Location details are updated in the list. | Location details are updated in the list. | Passed
|  | T1.3 | Admin deletes a location | 1. Location exists (Gaza Office). | the date of saved location | 1. Select the location. 2. Click Delete. 3. Confirm deletion. | Location is removed from the list. | Location is removed from the list. | Passed
|  | T1.4 | Admin searches for a location | 1. Multiple locations exist. | Search data: name or city or country | 1. Enter "Gaza office" in the search bar. 2. Click Search. | Only "Gaza Office" is displayed. | Only "Gaza Office" is displayed. | Passed
|  | T1.5 | Add location with missing mandatory fields | 1. Admin is logged in. | Name: (Blank) Country: (Blank) | 1. Click + Add. 2. Leave Name/Country blank. 3. Click Save. | Error message appears, not saved. | Error message appears, not saved. | Passed
|  | T1.6 | Edit location with invalid phone format | 1. Location exists. | Phone: 123-ABC-4567 | 1. Edit the location. 2. Enter invalid phone. 3. Click Save. | Error prompts for valid phone format , not saved. | Error prompts for valid phone format , not saved. | Passed
|  | T1.7 | Delete a location with assigned employees | 1. Location has employees | information of location with employess | 1. Attempt to delete the location. | System prevents deletion (warning message). | the system delete the location without warning message | Failed | B4
|  | T1.8 | Add location with more maximum field length | 1. Admin is logged in. | Name: A.repeat(255) City: B.repeat(100) | 1. Enter max-length data. 2. Click Save. | Record is not saved | the system doesn't accpet the records and the warning messages appear | Passed
|  | T1.9 | Search with special characters | 1. Locations exist. | Search Term: @#$% | 1. Enter special characters. 2. Click Search. | No results | No results | Passed
|  | T1.10 | Edit country to a non-listed value | 1. Location exists. | Country: Mars | 1. Attempt to edit Country to an invalid value. | Dropdown restricts to valid countries. | Dropdown restricts to valid countries. | Passed
R3.2.3.3 | Structure feature | T2.1 | Admin adds a new unit under parent company | 1. Admin is logged in. 2. "Structure" page is accessible. 3. edit option is enable | Unit ID ,Unit Name ,Description | 1. Navigate to Admin > Organization > Structure. 2. Click Edit then Add. 3. Enter valid data. 4. Click Save. | New unit appears under the parent company (OrangeHRM). | New unit appears under the parent company (OrangeHRM). | Passed
|  | T2.2 | Admin adds a sub-unit under an existing unit | 1. Unit exists (e.g., Administration). | Sub-unit Name: HR Team Description: Recruitment and employee management | 1. Click [+] next to Administration. 2. Click Add. 3. Enter valid data. 4. Click Save. | Sub-unit appears under Administration in the hierarchy. | Sub-unit appears under Administration in the hierarchy. | Passed
|  | T2.3 | Admin edits a unit’s details | 1. Unit exists (e.g., Engineering). | Updated Name: R&D Engineering | 1. Select Engineering. 2. Click Edit. 3. Update name. 4. Click Save. | Unit details are updated in the structure. | Unit details are updated in the structure. | Passed
|  | T2.4 | Admin deletes a unit | 1. Unit exists (e.g., Client Services). | Unit Name: Client Services | 1. Click Delete next to the unit. 2. Confirm deletion. | Unit is removed from the structure. | Unit is removed from the structure. | Passed
|  | T2.5 | Admin collapses/expands units | 1. Units with sub-units exist. | ---- | 1. Click Collapse (˅) next to a unit. 2. Click Expand (>). | Sub-units are hidden/shown as expected. | Sub-units are hidden/shown as expected. | Passed
|  | T2.6 | Add unit with missing mandatory fields | 1. Admin is logged in. | Unit Name: (Blank) | 1. Click Add. 2. Leave Name blank. 3. Click Save. | Error message appears; unit not saved. | Error message appears; unit not saved. | Passed
|  | T2.7 | Delete a unit with sub-units | 1. Unit has sub-units (e.g., Administration). | Unit Name: Administration | 1. Attempt to delete the unit. | System prevents deletion (warning message). | the system delete the unit with no warning message | Failed | B5
|  | T2.8 | Edit unit with invalid characters | 1. Unit exists. | Unit Name: Finance@#$ | 1. Edit unit. 2. Enter invalid name. 3. Click Save. | Error prompts for valid input. | the system accept the name | Failed | B6
|  | T2.9 | Add unit with more maximum field length | 1. Admin is logged in. | Unit Name: A.repeat(255) Description: B.repeat(500) | 1. Enter max-length data. 2. Click Save. | Unit is not saved | the system doesn't accpet the edit | Passed
|  | T2.10 | Add multiple nested sub-units (5+ levels) | 1. Parent unit exists. | Sub-unit Names: Level 1, Level 2, ..., Level 5 | 1. Add sub-units recursively under each level. | Hierarchy is displayed correctly without UI breaks. | Hierarchy is displayed correctly without UI breaks. | Passed
|  | T2.11 | Search for a unit with special characters | 1. Units exist. | Search Term: @Engineering | 1. Enter special characters in search. | System handles input gracefully (no errors). | System handles input gracefully (no errors). | Passed
R3.2.4.1 | Skills feature | T3.1 | Admin adds a new skill | 1. Admin is logged in. 2. "Skills" page is accessible. | Name: Project Management Description: Agile and Scrum methodologies | 1. Navigate to Admin > Qualifications > Skills. 2. Click + Add. 3. Enter valid data. 4. Click Save. | New skill appears in the skills list. | New skill appears in the skills list. | Passed
|  | T3.2 | Admin edits an existing skill | 1. Skill exists (e.g., Content Creation). | Updated Description: Digital Marketing Skill | 1. Click Edit next to the skill. 2. Update description. 3. Click Save. | Skill details are updated in the list. | Skill details are updated in the list. | Passed
|  | T3.3 | Admin deletes a single skill | 1. Skill exists (e.g., G Suite). | Name: G Suite | 1. Click Delete next to the skill. 2. Confirm deletion. | Skill is removed from the list. | Skill is removed from the list. | Passed
|  | T3.4 | Admin deletes multiple skills | 1. Multiple skills exist. | Selected Skills: Content Creation, G Suite | 1. Check skills to delete. 2. Click Delete Selected. 3. Confirm deletion. | Selected skills are removed. | Selected skills are removed. | Passed
|  | T3.5 | Admin views all skills | 1. Skills exist in the system. | --- | 1. Navigate to Skills page. | All skills are displayed in a paginated list. | All skills are displayed in a paginated list. | Passed
|  | T3.6 | Add skill with missing mandatory field (Name) | 1. Admin is logged in. | Name: (Blank) Description: Valid description | 1. Click + Add. 2. Leave Name blank. 3. Click Save. | Error message appears; skill not saved. | Error message appears; skill not saved. | Passed
|  | T3.7 | Edit skill with invalid data (special characters) | 1. Skill exists. | Name: Python#@! | 1. Edit skill. 2. Enter invalid name. 3. Click Save. | Error prompts for valid input. | the system accept the edit | Failed | B6 | Same bug as TC2.7
|  | T3.8 | Add skill with more than maximum field length | 1. Admin is logged in. | Name: A.repeat(255) Description: B.repeat(500) | 1. Enter max-length data. 2. Click Save. | Skill is not saved . | the system doesn't save the skill | Passed
|  | T3.9 | Bulk delete all skills | 1. Multiple skills exist. | Select All: True | 1. Select all skills. 2. Click Delete Selected. 3. Confirm deletion. | All skills are removed | All skills are removed | Passed
R3.2.4.2 | Education feature | T4.1 | Admin adds a new education level | 1. Admin is logged in. 2. "Education" page is accessible. | Level: Doctorate | 1. Navigate to Admin > Qualifications > Education. 2. Click + Add. 3. Enter valid data. 4. Click Save. | New education level appears in the list. | New education level appears in the list. | Passed
|  | T4.2 | Admin edits an existing education level | 1. Education level exists (e.g., Bachelor’s Degree). | Updated Level: Bachelor of Science | 1. Click Edit next to the education level. 2. Update the field. 3. Click Save. | Education level is updated in the list. | Education level is updated in the list. | Passed
|  | T4.3 | Admin deletes a single education level | 1. Education level exists (e.g., College Undergraduate). | Level: College Undergraduate | 1. Click Delete next to the education level. 2. Confirm deletion. | Education level is removed from the list. | Education level is removed from the list. | Passed
|  | T4.4 | Admin deletes multiple education levels | 1. Multiple education levels exist. | Selected Levels: High School Diploma, Master’s Degree | 1. Check levels to delete. 2. Click Delete Selected. 3. Confirm deletion. | Selected levels are removed. | Selected levels are removed. | Passed
|  | T4.5 | Admin views all education levels | 1. Education levels exist in the system. | ---- | 1. Navigate to Education page. | All levels are displayed in a paginated list. | All levels are displayed in a paginated list. | Passed
|  | T4.6 | Add education level with missing mandatory field | 1. Admin is logged in. | Level: (Blank) | 1. Click + Add. 2. Leave Level blank. 3. Click Save. | Error message appears; record not saved. | Error message appears; record not saved. | Passed
|  | T4.7 | Edit education level with invalid data (special characters) | 1. Education level exists. | Level: PhD@#$ | 1. Edit the level. 2. Enter invalid data. 3. Click Save. | Error prompts for valid input. | the system accept the name | Failed | B6 | Same bug as TC2.7
|  | T4.8 | Add education level with more than maximum field length | 1. Admin is logged in. | Level: A.repeat(255) | 1. Enter max-length data. 2. Click Save. | Education level is not saved | the system doen't accept and not saved | Passed
|  | T4.9 | Add duplicate education level | 1. Education level exists (e.g., High School Diploma). | Level: High School Diploma | 1. Attempt to add the same level again. | System prevents duplication (error message). | System prevents duplication (error message). | Passed
|  | T4.10 | Bulk delete all education levels | 1. Multiple education levels exist. | Select All: True | 1. Select all levels. 2. Click Delete Selected. 3. Confirm deletion. | All levels are removed | All levels are removed | Passed
R3.2.4.3 | License feature | T5.1 | Admin adds a new license | 1. Admin logged in 2. Licenses page accessible | Name: AWS Certified Solutions Architect | 1. Navigate to Admin > Qualifications > Licenses 2. Click +Add 3. Enter name 4. Click Save | New license appears in licenses list | New license appears in licenses list | Passed
|  | T5.2 | Admin edits existing license | 1. License exists (e.g., CDMP) | Updated Name: Certified Digital Marketing Pro | 1. Click Edit next to license 2. Update name 3. Click Save | License details updated in list | License details updated in list | Passed
|  | T5.3 | Admin deletes single license | 1. License exists (e.g., CCNA) | Name: Cisco Certified Network Associate | 1. Click Delete next to license 2. Confirm deletion | License removed from list | License removed from list | Passed
|  | T5.4 | Admin deletes multiple licenses | 1. Multiple licenses exist | Selected: CISM, MCSE | 1. Check licenses to delete 2. Click Delete Selected 3. Confirm | Selected licenses removed | Selected licenses removed | Passed
|  | T5.5 | Admin views all licenses | 1. Licenses exist in system | ----- | 1. Navigate to Licenses page | All licenses displayed in paginated list | All licenses displayed in paginated list | Passed
|  | T5.6 | Add license with missing name | 1. Admin logged in | Name: (Blank) | 1. Click +Add 2. Leave name blank 3. Click Save | Error appears; license not saved | Error appears; license not saved | Passed
|  | T5.7 | Edit license with invalid characters | 1. License exists | Name: PMI@ACP! | 1. Edit license 2. Enter invalid name 3. Click Save | Error prompts for valid input | the system accept the name | Failed | B6 | Same bug as TC2.7
|  | T5.8 | Add license with more than max length name | 1. Admin logged in | Name: A.repeat(255) | 1. Enter max-length name 2. Click Save | License not saved | the system doesn't accept the name and not saved | Passed
|  | T5.9 | Add duplicate license name | 1. License exists (MCSE) | Name: Microsoft Certified Systems Engineer | 1. Attempt to add same name | System prevents duplication | System prevents duplication | Passed
|  | T5.10 | Bulk delete all licenses | 1. Multiple licenses exist | Select All: True | 1. Select all 2. Delete Selected 3. Confirm | All licenses removed | All licenses removed | Passed
R3.2.4.4 | Languages feature | T6.1 | Admin adds a new language | 1. Admin logged in 2. Languages page accessible | Name: German | 1. Navigate to Admin > Qualifications > Languages 2. Click +Add 3. Enter name 4. Click Save | New language appears in list | New language appears in list | Passed
|  | T6.2 | Admin edits existing language | 1. Language exists (e.g., Chinese) | Updated Name: Mandarin | 1. Click Edit next to language 2. Update name 3. Click Save | Language details updated | Language details updated | Passed
|  | T6.3 | Admin deletes single language | 1. Language exists (e.g., Arabic) | Name: Arabic | 1. Click Delete next to language 2. Confirm deletion | Language removed from list | Language removed from list | Passed
|  | T6.4 | Admin deletes multiple languages | 1. Multiple languages exist | Selected: French, Russian | 1. Check languages to delete 2. Click Delete Selected 3. Confirm | Selected languages removed | Selected languages removed | Passed
|  | T6.5 | Admin views all languages | 1. Languages exist in system | ---- | 1. Navigate to Languages page | All languages displayed | All languages displayed | Passed
|  | T6.6 | Add language with missing name | 1. Admin logged in | Name: (Blank) | 1. Click +Add 2. Leave name blank 3. Click Save | Error appears; not saved | Error appears; not saved | Passed
|  | T6.7 | Edit language with invalid characters | 1. Language exists | Name: Engl!sh@ | 1. Edit language 2. Enter invalid name 3. Click Save | Error prompts for valid input | the system accept the name | Failed | B6 | Same bug as TC2.7
|  | T6.8 | Add language with more than max length name | 1. Admin logged in | Name: A.repeat(255) | 1. Enter max-length name 2. Click Save | Language not saved | the system doesn't accept the repeatation | Passed
|  | T6.9 | Add duplicate language | 1. Language exists (Spanish) | Name: Spanish | 1. Attempt to add same name | System prevents duplication | System prevents duplication | Passed
|  | T6.10 | Bulk delete all languages | 1. Multiple languages exist | Select All: True | 1. Select all 2. Delete Selected 3. Confirm | All languages removed | All languages removed | Passed
R3.2.4.5 | Memberships feature | T7.1 | Admin adds new membership | 1. Admin logged in 2. Memberships accessible | Name: PMP | 1. Navigate to Admin > Qualifications > Memberships 2. Click +Add 3. Enter name 4. Click Save | New membership appears in list | New membership appears in list | Passed
|  | T7.2 | Admin edits existing membership | 1. Membership exists (ACCA) | Updated Name: ACCA Global | 1. Click Edit next to membership 2. Update name 3. Click Save | Membership details updated | Membership details updated | Passed
|  | T7.3 | Admin deletes single membership | 1. Membership exists (CIM) | Name: Chartered Institute of Marketing | 1. Click Delete next to membership 2. Confirm deletion | Membership removed from list | Membership removed from list | Passed
|  | T7.4 | Admin deletes multiple memberships | 1. Multiple memberships exist | Selected: BCS, CIMA | 1. Check memberships to delete 2. Click Delete Selected 3. Confirm | Selected memberships removed | Selected memberships removed | Passed
|  | T7.5 | Admin views all memberships | 1. Memberships exist | ---- | 1. Navigate to Memberships page | All memberships displayed | All memberships displayed | Passed
|  | T7.6 | Add membership with blank name | 1. Admin logged in | Name: (Blank) | 1. Click +Add 2. Leave name blank 3. Click Save | Error appears; not saved | Error appears; not saved | Passed
|  | T7.7 | Edit membership with invalid characters | 1. Membership exists | Name: CIM@2025! | 1. Edit membership 2. Enter invalid name 3. Click Save | Error prompts for valid input | the system accept the name | Failed | B6 | Same bug as TC2.7
|  | T7.8 | Add membership with more than max length name | 1. Admin logged in | Name: A.repeat(255) | 1. Enter max-length name 2. Click Save | Membership not saved | the system doesn't accept the repeatation | Passed
|  | T7.9 | Add duplicate membership | 1. Membership exists (BCS) | Name: British Computer Society | 1. Attempt to add same name | System prevents duplication | System prevents duplication | Passed
|  | T7.10 | Bulk delete all memberships | 1. Multiple memberships exist | Select All: True | 1. Select all 2. Delete Selected 3. Confirm | All memberships removed | All memberships removed | Passed

## Bug Reports (Employee)
Employee
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B7 | Add Work Experience with Future Date | System accepts future date without validation | Browser: Chrome Windows 11 Laptop-Asus | Medium | Major | 1. Go to My Info > Qualifications > Work Experience 2. Click "Add" 3. Set From Date to 01/01/2026 4. Click "Save" | Validation error: "Date cannot be in the future" | Entry is added successfully without validation error | Data inconsistency | https://www.awesomescreenshot.com/image/55321141?key=56f7c22da1edf2f2d63c43809c8719be
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B8 | Delete Education Entry Fails | Existing education entry cannot be deleted | Browser: Chrome Windows 11 Laptop-Asus | High | Major | 1. Go to Education section 2. Select an existing entry 3. Click "Delete" | Entry is deleted successfully from the list | Error message: "Entry does not exist" appears even though the entry exists | Functional | https://www.awesomescreenshot.com/image/55321140?key=81878a7e85e270cf95ddccffff8b3a3d , https://www.awesomescreenshot.com/image/55321158?key=7c0c415bdea7cc08b7c842cfeb57f407
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B9 | GPA/Score accepts alphabetic input | System allows non-numeric GPA input | Browser: Chrome Windows 11 Laptop-Asus | Medium | Moderate | 1. Go to My Info > Qualifications > Education 2. Click "Add" 3. Enter "twenty twenty" as Year 4. Click "Save" | Validation error: "Enter numbers only" | Entry is saved successfully with alphabetic characters | Input validation missing | https://www.awesomescreenshot.com/image/55321142?key=fa488ca2a1aa63c43cddfcf002abbe39
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B1 | Account Lockout Not Triggered After Multiple Failed Login Attempts | The system allows repeated failed login attempts without locking the account or displaying a security warning | Browser: Edge Windows 11 Laptop-Asus | High | Moderate | 1. Enter wrong password multiple times 2. Observe system behavior | System should lock account or display warning | No action was taken | This issue may pose a potential security risk | https://www.awesomescreenshot.com/image/55322047?key=08884bdd2a84c3efc90e0d249b6cb1ab
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof | Priority | Seviority
B2 | User Can Access Login Page After Authentication via Browser Back Button Without Logging Out | After successfully logging into the system, if the user clicks the browser's back button, the application navigates back to the login page without logging the user out. | Browser: Chrome Windows 11 Laptop-Asus | Low | Major | 1. Log in with valid credintals 2. click on browser back | System should not return to login page unless logged out | Login page reappeared but was unresponsive |  | https://www.awesomescreenshot.com/image/55322053?key=e484001756a38d99ed7a7e814113fe77 , https://www.awesomescreenshot.com/image/55322052?key=10fee35ae15d1053f332c2e7c4c10737 | Low | Minor
[11 empty] | Medium | Moderate
[11 empty] | High | Major
[11 empty] | Immediate | Critical
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B3 | The system accept invalid mobile number | In the "contact details" the system accept Just the number "5" as a phone number | Browser: Edge Windows 11 Laptop-Asus | Medium | Moderate | 1. Access 'My Info' > 'Contact Details' 2. Enter invalid phone format 3. Click 'Save' | System should reject input | invalid phone accepted |  | https://www.awesomescreenshot.com/image/55322051?key=1a4d5ecce765d896af3b3911d081b2e1
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B5 | Number Field Allows Alphabetic Characters in Immigration Section | In the "Immigration" the system accepts alphabetic input "ABD345"in the Number field, which is expected to allow numeric values only, as specified in the SRS document. | Browser: Edge Windows 11 Laptop-Asus | Medium | Moderate | 1. Go to 'Immigration' 2. Click 'Add' 3. Enter letters in Number field 4. Click 'Save' | System should reject it and display error message | Letters accepted in Number field |  | https://www.awesomescreenshot.com/image/55322050?key=451d9610d3331388d4d85b44a5f9d6a6
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B4 | State Field Does Not Change to Dropdown When "United States" is Selected | When the user selects "United States" as the country in the Contact Details form, the State field remains a text input instead of dynamically switching to a dropdown list of US states. | Browser: Edge Windows 11 Laptop-Asus | Medium | Moderate | 1. Access 'My Info' > 'Contact Details' 2. Select country = US | State field should become dropdown with US states list | Field remains manual input for all countries |  | https://www.awesomescreenshot.com/image/55322049?key=92ded428100790d0eb48aeb4ed2a155d
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B6 | "Issued Date" Field Accepts Future Dates Without Validation in Immigration Section | In the Immigration section of the My Info module, the system allows users to input future dates in the "Issued Date" field without displaying an error or validation message. | Browser: Edge Windows 11 Laptop-Asus | High | Moderate | 1. Go to My Info > Immigration 2. Enter a future Issued Date | System should reject future dates with error message | Future date accepted with no validation |  | https://www.awesomescreenshot.com/image/55322048?key=046445f907e63af9393a84c2843f640c

## Bug Reports (Admin)
Admin
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof | Priority | Seviority
B1 | Employee Name field incorrectly uses a dropdown instead of a text input | Cant create employee name when adding user, because employee name is restricted by dropdown lists (You need type for hints) | Platform: Lenovo Laptop Browser: Brave OS: Windows 10 | Immediate | Moderate | 1. Login as admin 2. Open admin module 3. Add button 4. Employee Name | Text lable | Drop down list lable | Repeated in TC1, TC20 | https://www.awesomescreenshot.com/image/55255170?key=d5ec43810151e40105f28eecae3ce8d8 | Low | Minor
[11 empty] | Medium | Moderate
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof | High | Major
B2 | Job Title field accepts special characters and numbers | The Job Title field currently allows input of special characters and numeric values. This can lead to data inconsistencies and unprofessional entries. Input validation is missing. | Platform: Lenovo Laptop Browser: Brave OS: Windows 10 | Low | Minor | 1. Login as admin 2. Open job module 3. add/edit job 4. job title | Warning Message: "Cant use characters in Username" + No Save | Label Accept the username | Repeated in TC32, TC35 | https://www.awesomescreenshot.com/image/55255171?key=066d911fdc085df569b0fac180c0c972 | Immediate | Critical
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B3 | Employee Status field accepts special characters and numbers | Employment Status field currently allows input of special characters and numeric values. This can lead to data inconsistencies and unprofessional entries. Input validation is missing. | Platform: Lenovo Laptop Browser: Brave OS: Windows 10 | Low | Minor | 1. Login as admin 2. Open admin page 3. Employement Status 4. Add/Edit 5. name | Warning Message Cant include special chars except "-" | Accepted | - For Example: Fullt@@TIME - Repeated in TC55, TC 64 | https://www.awesomescreenshot.com/image/55255172?key=abdb0f966033088ed832065166c1cf1f
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B4 | System allows deletion of a location with assigned employees without warning | The system permits deletion of a location (company) that has employees assigned to it, without displaying any warning or confirmation message. This may lead to accidental data loss or orphaned employee records. | Platform: HP Laptop Browser: Chrome OS: Windows 10 | Medium | Moderate | 1. Login as admin 2. Open admin page 3. Organization then locations 4. select company with employess 5. delete | warning message before delete | the system delete the company with employess without any warning message | Repeated in TC 1.7 | https://www.awesomescreenshot.com/video/41419138?key=21ff22e3f884c0373bf0bd1bbb741a47
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B5 | System allows deletion of a unit containing sub-units without warning | The system permits deletion of an organizational unit that contains sub-units without displaying any confirmation or warning message. This can result in accidental data loss and compromised organizational structure. | Platform: HP Laptop Browser: Chrome OS: Windows 10 | High | Moderate | 1. Navigate to Admin > Organization > Structure. 2. Click Edit then the system shows the units. 3. delete unit contain sub units | warning message before delete | the system delete the unit with sub units without any warning message | Repeated in TC 2.7 | https://www.awesomescreenshot.com/video/41419119?key=ee8ffcf0963b26fc9d6289283c13c24f
Bug ID | Title | Summary | Environment | Priority | Severity | Steps to Reproduce | Expected Resutls | Actual Resutls | Notes | Visual Proof
B6 | System accepts invalid characters in various Admin features (Locations, Structure, Education, Memberships, Licenses, and Languages) | The system allows users to input and save special characters in required fields during Add, Edit, and Search operations across multiple features without any validation or restriction. This behavior can lead to data inconsistency and potential security risks such as injection attacks. | Platform: HP Laptop Browser: Chrome OS: Windows 10 | Medium | Moderate | 1. Navigate to Admin > the feature . 2. Click Edit, add or search 3. Enter special characters in search bar or required field in add or edit operation . | the system must prevention having spiecal characters in required fildes | the system accept having spiecal characters in required fildes | Repeated in 2.8 , 3.7 , 4.7, 5.7, 6.7, 7.7 | https://www.awesomescreenshot.com/image/55255171?key=066d911fdc085df569b0fac180c0c972

## RTM (Employee)
Requirement Traceability Matrix (RTM)
Req ID | Requirement Name | Reuirement Description | Test Case ID | Assigned To | Current Status
"3.0 | Login | ESS-User can log in with a valid username and password provided by the HR Admin | 3.0.1, 3.0.2, 3.0.3, 3.0.4, 3.0.5, 3.0.6, 3.0.7, 3.0.8, 3.0.9, 3.0.10, 3.0.11, 3.0.12, 3.0.13 | Mohammad Foqahaa | Complete
3.1.1 | Personal Details | The ESS-User can add/edit their personal information details. | 3.1.1.1, 3.1.1.2, 3.1.1.3, 3.1.1.4, 3.1.1.5, 3.1.1.6, 3.1.1.7, 3.1.1.8, 3.1.1.9, 3.1.1.10, 3.1.1.11, 3.1.1.12, 3.1.1.13, 3.1.1.14, 3.1.1.15, 3.1.1.16 |  |  | Statuses:
3.1.2 | Photograph | The ESS-User can add/edit their profile photo. | 3.1.2.1, 3.1.2.2, 3.1.2.3, 3.1.2.4 |  |  | Not Started
3.1.3 | Contact Details | The ESS-User can add/edit their Contact Details. | 3.1.3.1, 3.1.3.2, 3.1.3.3, 3.1.3.4, 3.1.3.5, 3.1.3.6, 3.1.3.7, 3.1.3.8, 3.1.3.9, 3.1.3.10, 3.1.3.11, 3.1.3.12 |  |  | Elaboration
3.1.4 | Emergency Contact | The ESS-User can add/delete their Emergency Contact details and upload supporting documents. | 3.1.4.1, 3.1.4.2, 3.1.4.3, 3.1.4.4, 3.1.4.5, 3.1.4.6, 3.1.4.7, 3.1.4.8, 3.1.4.9, 3.1.4.10, 3.1.4.11, 3.1.4.12, 3.1.4.13, 3.1.4.14 |  |  | Development
3.1.5 | Dependents | The ESS-User can add/delete their Dependents details and upload supporting documents. | 3.1.5.1, 3.1.5.2, 3.1.5.3, 3.1.5.4, 3.1.5.5, 3.1.5.6, 3.1.5.7, 3.1.5.8, 3.1.5.9, 3.1.5.10, 3.1.5.11, 3.1.5.12, 3.1.5.13, 3.1.5.14, 3.1.5.15 |  |  | Testing
3.1.6 | Immigration | The ESS-User can add/delete their Immigration details and upload supporting documents. | 3.1.6.1, 3.1.6.2, 3.1.6.3, 3.1.6.4, 3.1.6.5, 3.1.6.6, 3.1.6.7, 3.1.6.8, 3.1.6.9, 3.1.6.10, 3.1.6.11, 3.1.6.12, 3.1.6.13, 3.1.6.14, 3.1.6.15 |  |  | Complete
3.1.7 | Job Details | The ESS-User has to be able to view job details, So that he can see important employment information without being able to change it. | 3.1.7.1, 3.1.7.2, 3.1.7.3, 3.1.7.4, 3.1.7.5 | Nagham Taweel | Complete
3.1.8 | Salary | The salary details section of the ESS-User, has to be completely hidden , So that confidential salary information is protected and only accessible by the HR Admin. | 3.1.8.1, 3.1.8.2, 3.1.8.3, 3.1.8.4
3.1.9 | Report To | The ESS-User, has to be able to view the list of assigned supervisors (and subordinates if he's a supervisor). | 3.1.9.1, 3.1.9.2, 3.1.9.3, 3.1.9.4
3.1.10 | Qualifications | The ESS-User, can manage (add, update, and delete) his qualifications — including Work Experience, Education, Skills, Languages, Licenses, and Attachments. | 3.1.10.1, 3.1.10.2, 3.1.10.3, 3.1.10.4, 3.1.10.5, 3.1.10.6, 3.1.10.7, 3.1.10.8, 3.1.10.9, 3.1.10.10, 3.1.10.11, 3.1.10.12, 3.1.10.13, 3.1.10.14, 3.1.10.15, 3.1.10.16, 3.1.10.17, 3.1.10.18, 3.1.10.19, 3.1.10.20, 3.1.10.21, 3.1.10.22, 3.1.10.23, 3.1.10.24, 3.1.10.25, 3.1.10.26, 3.1.10.27, 3.1.10.28, 3.1.10.29, 3.1.10.30
3.1.11 | Membership | The ESS-User, can add, update, and delete his membership details and upload supporting attachments. | 3.1.11.1, 3.1.11.2, 3.1.11.3, 3.1.11.4, 3.1.11.5, 3.1.11.6, 3.1.11.7, 3.1.11.8, 3.1.11.9, 3.1.11.10, 3.1.11.11, 3.1.11.12, 3.1.11.13

## RTM (Admin)
Requirement Traceability Matrix (RTM)
Req ID | Requirement Name | Reuirement Description | Test Case ID | Assigned To | Current Status
R3.2.1 | User Management Module | Admin create user accounts with roles (Admin/ESS), and can edit or delete user accounts. | TC1, TC2, TC3, TC4, TC5, TC6, TC7, TC8, TC9, TC10, TC11, TC12, TC13, TC14, TC15, TC16, TC17, TC18, TC19, TC20, TC21, TC22, TC23, TC24, TC25, TC26 | Abdelrahman Murad | Complete
R3.2.2.1 | Job Titles | Admin can add/edit/delete job titles | TC27, TC28, TC29, TC30, TC31, TC32, TC33, TC34, TC35, TC36, TC37, TC38, TC39 |  |  | Statuses:
R3.2.2.2 | Pay Grades | Admin can add/edit/delete pay grades with identifying salary ranges. | TC40, TC41, TC42, TC43, TC44, TC45, TC46, TC47, TC48, TC49, TC50, TC51 |  |  | Not Started
R3.2.2.3 | Employment Status | Admin can add/edit/delete employment status. | TC52, TC53, TC54, TC55, TC56, TC57, TC58, TC59, TC60 |  |  | Elaboration
R3.2.2.4 | Job Categories | Admin can create/edit/delete job categories. | TC61, TC62, TC63, TC64, TC65, TC66, TC67, TC68, TC69 |  |  | Development
R3.2.2.5 | Work Shifts | Admin can assign work shirts for employees. | TC70, TC71, TC72, TC73, TC74, TC75, TC76, TC77, TC78, TC79 |  |  | Testing
R3.2.3.1 | General Information | Admin can edit companies general information. | TC80, TC81, TC82, TC83, TC84, TC85, TC86, TC87, TC88 |  |  | Complete
R3.2.3.2 | Locations | the admin control the Locations feature and perform opreations related to it like (search, add , edit , delete , view ) | TC (1.1, 1.2 , 1.3, 1.4 , 1.5 , 1.6 , 1.7 , 1.8 , 1.9 , 1.11 ) | Haya | Complete
R3.2.3.3 | Structure | the admin control the Structure feature and perform opreations related to the units and sub units like (search, expand, collapes, add , edit , delete , view ) | TC (2.1, 2.2 , 2.3, 2.4 , 2.5 , 2.6 , 2.7 , 2.8 , 2.9 , 2.11 , 2.12)
R3.2.4.1 | Skills | the admin control the skills feature and perform opreations related to it like ( add , edit , delete , view ) | TC (3.1, 3.2 , 3.3, 3.4 , 3.5 , 3.6 ,3.7 , 3.8 , 3.9 , 3.11 )
R3.2.4.2 | Education | the admin control the Education feature and perform opreations related to it like ( add , edit , delete , view ) | TC (4.1, 4.2 , 4.3, 4.4 , 4.5 , 4.6 ,4.7 , 4.8 ,4.9 , 4.11 )
R3.2.4.3 | License | the admin control the License feature and perform opreations related to it like add , edit , delete , view ) | TC (5.1, 5.2 , 5.3, 5.4 , 5.5 , 5.6 ,5.7 , 5.8 ,5.9 , 5.11 )
R3.2.4.4 | Languages | the admin control the Languages feature and perform opreations related to it like (, add , edit , delete , view ) | TC (6.1,6.2 , 6.3, 6.4 , 6.5 ,6.6 ,6.7 , 6.8 ,6.9 , 6.11 )
R3.2.4.5 | Memberships | the admin control the Memberships feature and perform opreations related to it like (add , edit , delete , view ) | TC (7.1,7.2 , 7.3, 7.4 , 7.5 ,7.6 ,7.7 , 7.8 ,7.9 , 7.11 )

## Test Summary Report
Test Report
Test Cycle | System Test
Executed | Passed |  |  |  | 287
| Failed |  |  |  | 15
| Total Tests Executed (Passed + Failed) |  |  |  |  | 302 | Total Tc's | 302
Pending | [5 empty] | 0 | Passed | 287
In Progress | [5 empty] | 0 | Failed | 15 | Total TCs | 305
Blocked | [5 empty] | 1 | Blocked | 1 | Passed | 288
(Sub-Total) Test Planed | [5 empty] | 302 |  |  | Failed | 16
[Pending - In Progress - Blocked - Test Executed] | [8 empty] | Blocked | 1
Functions (Test Scenarios) | Description | TCs Excuted % | TCs Passed % | TCs pending | Priority | Remarks
Login | ESS-User can log in with a valid username and password provided by the HR Admin | 100% | 85% | 0% | High
Personal Details | The ESS-User can add/edit their personal information details. | 100% | 100% | 0% | High
Photograph | The ESS-User can add/edit their profile photo. | 100% | 100% | 0% | Low
Contact Details | The ESS-User can add/edit their Contact Details. | 100% | 92% | 0% | High
Emergency Contact | The ESS-User can add/delete their Emergency Contact details and upload supporting documents. | 100% | 100% | 0% | High
Dependents | The ESS-User can add/delete their Dependents details and upload supporting documents. | 100% | 100% | 0% | Medium
Immigration | The ESS-User can add/delete their Immigration details and upload supporting documents. | 100% | 93% | 0% | Medium
Job Details | The ESS-User is able to view job details, without being able to change it. | 100% | 100% | 0% | High
Salary | The salary details section of the ESS-User is completely hidden So that , salary information is protected and only accessible by the HR Admin. | 100% | 75% | 0% | High
Report To | The ESS-User, is able to view the list of assigned supervisors (and subordinates if he's a supervisor). | 100% | 100% | 0% | Medium
Qualifications | The ESS-User, can manage (add, update, and delete) his qualifications — including Work Experience, Education, Skills, Languages, Licenses, and Attachments. | 100% | 90% | 0% | High
Membership | The ESS-User, can add, update, and delete his membership details and upload supporting attachments. | 100% | 100% | 0% | Low
User Management Module | Admin create user accounts with roles (Admin/ESS), and can edit or delete user accounts. | 100% | 92% | 0% | High
Job Titles | Admin can add/edit/delete job titles | 100% | 77% | 0% | High
Pay Grades | Admin can add/edit/delete pay grades with identifying salary ranges. | 100% | 100% | 0% | High
Employment Status | Admin can add/edit/delete employment status. | 100% | 88% | 0% | High
Job Categories | Admin can create/edit/delete job categories. | 100% | 88% | 0% | High
Work Shifts | Admin can assign work shirts for employees. | 100% | 100% | 0% | High
General Information | Admin can edit companies general information. | 100% | 89% | 0% | Medium
Locations | the admin control the Locations feature and perform opreations related to it like (search, add , edit , delete , view ) | 100% | 90% | 0% | High
Structure | the admin control the Structure feature and perform opreations related to the units and sub units like (search, expand, collapes, add , edit , delete , view ) | 100% | 82% | 0% | High
Skills | the admin control the skills feature and perform opreations related to it like ( add , edit , delete , view ) | 100% | 89% | 0% | High
Education | the admin control the Education feature and perform opreations related to it like ( add , edit , delete , view ) | 100% | 90% | 0% | Medium
License | the admin control the License feature and perform opreations related to it like add , edit , delete , view ) | 100% | 90% | 0% | High
Languages | the admin control the Languages feature and perform opreations related to it like (, add , edit , delete , view ) | 100% | 90% | 0% | Medium
Memberships | the admin control the Memberships feature and perform opreations related to it like (add , edit , delete , view ) | 100% | 90% | 0% | High